## Grand Summary
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2022/14
MODIFICATION WORKS OF NOISE BARRIERS ALONG YUEN LONG HIGHWAY NEAR PARK SIGNATURE
GRAND SUMMARY OF
THE ACTIVITY SCHEDULE
Page | Description |  |  | Amount (HK$)
AS.S1/16 |  | Schedule No. 1 - Preliminaries |  | $
AS.S2/01 |  | Schedule No. 2 - Preservation and Protection of Trees |  | $
AS.S3/05 |  | Schedule No. 3 - Modification Works of Noise Barriers |  | $
AS.S4/03 |  | Schedule No. 4 - Monitoring Payment of Wages |  | $
AS.S5/10 |  | Schedule No. 5 - Site Safety |  | $ | 252780
AS.S6/03 |  | Schedule No. 6 - Site Cleanliness and Tidiness |  | $ | 419322
|  | Sub-total of above (A) |  | $
|  | Tendered total of the Prices = (A) [To be carried to the Form of Tender and the Contract Data Part two subject to the correction rules for tender errors as set out in Clause GCT 11 of the General Conditions of Tender] |  | $
|  | Contingency sum for Defined Cost for compensation events* (B) |  | $ | 2100000
|  | Contingency sum for Fee for compensation events* (C) = (B) x fee percentage inserted by the tenderer in the Contract Data Part two |  | $
|  | Provisional sum for price adjustment for inflation under Secondary Option X1* (D) |  | $ | 945000
|  | Provisional sum for performance‐tied payment item under Pay for Safety Performance Merit Scheme (PFSPMS) under Secondary Option X20* (E) |  | $ | 336188
Sub‐total of all contingency sums and provisional sums above* (F) = (B) + (C) + (D) + (E)
|  | Forecast total of the Prices for tender evaluation purpose* (G) = (A) + (F) |  | To be completed by the Project Manager designate after receipt of tender
*Remarks: The contingency sums, provisional sums and forecast total of the Prices shall not form part of this contract. Please refer to Clause [A7] of the additional conditions of contract.
(1) The contingency sums, provisional sums and forecast total of the Prices shall not form part of the contract. Please refer to Clause A7 of the additional conditions of contract.
Signature of person authorised
| to sign on behalf of tenderer : |  | ……………………………………………………
| Name of Tenderer: |  | ……………………………………………………
| Date: |  | ……………………………………………………
[BLANK PAGE]

## A1
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2022/14
MODIFICATION WORKS OF NOISE BARRIERS ALONG YUEN LONG HIGHWAY NEAR PARK SIGNATURE
ACTIVITY SCHEDULE
Schedule No. 1 - Preliminaries
Item | Activity |  | Prices (HK$)
1.1 | Temporary Accommodation for the Project Manager and Supervisor
1.1.1 | Provision of the temporary accommodation for the Project Manager and Supervisor to the satisfaction of the Project Manager |  | $
1.1.2 | Provision of all furniture required by this contract to enable operation |  | $
1.1.3.1 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 1st calendar month |  | $
1.1.3.2 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 2nd calendar month |  | $
1.1.3.3 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 3rd calendar month |  | $
1.1.3.4 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 4th calendar month |  | $
1.1.3.5 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 5th calendar month |  | $
1.1.3.6 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 6th calendar month |  | $
1.1.3.7 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 7th calendar month |  | $
1.1.3.8 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 8th calendar month |  | $
1.1.3.9 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 9th calendar month |  | $
1.1.3.10 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 10th calendar month |  | $
1.1.3.11 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 11th calendar month |  | $
1.1.3.12 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 12th calendar month |  | $
1.1.3.13 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 13th calendar month |  | $
1.1.3.14 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 14th calendar month |  | $
1.1.3.15 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 15th calendar month |  | $
1.1.3.16 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 16th calendar month |  | $
1.1.3.17 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 17th calendar month |  | $
1.1.3.18 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 18th calendar month |  | $
1.1.3.19 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 19th calendar month |  | $
1.1.3.20 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 20th calendar month |  | $
1.1.3.21 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 21st calendar month |  | $
1.1.3.22 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 22nd calendar month |  | $
1.1.3.23 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 23rd calendar month |  | $
1.1.3.24 | Fulfilling the obligations of maintenance of temporary accommodation provided for the 24th calendar month |  | $
1.1.4 | Demolition, clear and reinstatement of the area occupied by temporary accommodation and handover to the Client |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.2 | Temporary Accommodation for the Contractor
1.2.1 | Provision of the temporary accommodation including workshops, offices, storage sheds and security system for the Contractor to the satisfaction of the Project Manager |  | $
1.2.2 | Provision of all furniture required by this contract to enable operation |  | $
1.2.3.1 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 1st calendar month |  | $
1.2.3.2 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 2nd calendar month |  | $
1.2.3.3 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 3rd calendar month |  | $
1.2.3.4 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 4th calendar month |  | $
1.2.3.5 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 5th calendar month |  | $
1.2.3.6 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 6th calendar month |  | $
1.2.3.7 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 7th calendar month |  | $
1.2.3.8 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 8th calendar month |  | $
1.2.3.9 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 9th calendar month |  | $
1.2.3.10 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 10th calendar month |  | $
1.2.3.11 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 11th calendar month |  | $
1.2.3.12 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 12th calendar month |  | $
1.2.3.13 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 13th calendar month |  | $
1.2.3.14 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 14th calendar month |  | $
1.2.3.15 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 15th calendar month |  | $
1.2.3.16 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 16th calendar month |  | $
1.2.3.17 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 17th calendar month |  | $
1.2.3.18 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 18th calendar month |  | $
1.2.3.19 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 19th calendar month |  | $
1.2.3.20 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 20th calendar month |  | $
1.2.3.21 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 21st calendar month |  | $
1.2.3.22 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 22nd calendar month |  | $
1.2.3.23 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 23rd calendar month |  | $
1.2.3.24 | Fulfilling the obligations of servicing of the Contractor's temporary accommodation for the 24th calendar month |  | $
1.2.4 | Demolition, clear and reinstatement of the area occupied by temporary accommodation and handover to the Client |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.3 | Computer Facilities for the Project Manager and Supervisor
1.3.1 | Provision of computer facilities required by this contract to enable operation |  | $
1.3.2.1 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 1st calendar month |  | $
1.3.2.2 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 2nd calendar month |  | $
1.3.2.3 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 3rd calendar month |  | $
1.3.2.4 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 4th calendar month |  | $
1.3.2.5 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 5th calendar month |  | $
1.3.2.6 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 6th calendar month |  | $
1.3.2.7 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 7th calendar month |  | $
1.3.2.8 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 8th calendar month |  | $
1.3.2.9 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 9th calendar month |  | $
1.3.2.10 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 10th calendar month |  | $
1.3.2.11 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 11th calendar month |  | $
1.3.2.12 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 12th calendar month |  | $
1.3.2.13 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 13th calendar month |  | $
1.3.2.14 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 14th calendar month |  | $
1.3.2.15 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 15th calendar month |  | $
1.3.2.16 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 16th calendar month |  | $
1.3.2.17 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 17th calendar month |  | $
1.3.2.18 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 18th calendar month |  | $
1.3.2.19 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 19th calendar month |  | $
1.3.2.20 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 20th calendar month |  | $
1.3.2.21 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 21st calendar month |  | $
1.3.2.22 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 22nd calendar month |  | $
1.3.2.23 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 23rd calendar month |  | $
1.3.2.24 | Fulfilling the obligations of maintenance and servicing of computer facilities for the 24th calendar month |  | $
1.3.3 | Provision of required computer facilities training |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.4 | Transport for the use of the Project Manager and Supervisor
1.4.1 | Provision of land transport |  | $
1.4.2.1 | Fulfilling the obligations of maintenance of land transport provided for the 1st calendar month |  | $
1.4.2.2 | Fulfilling the obligations of maintenance of land transport provided for the 2nd calendar month |  | $
1.4.2.3 | Fulfilling the obligations of maintenance of land transport provided for the 3rd calendar month |  | $
1.4.2.4 | Fulfilling the obligations of maintenance of land transport provided for the 4th calendar month |  | $
1.4.2.5 | Fulfilling the obligations of maintenance of land transport provided for the 5th calendar month |  | $
1.4.2.6 | Fulfilling the obligations of maintenance of land transport provided for the 6th calendar month |  | $
1.4.2.7 | Fulfilling the obligations of maintenance of land transport provided for the 7th calendar month |  | $
1.4.2.8 | Fulfilling the obligations of maintenance of land transport provided for the 8th calendar month |  | $
1.4.2.9 | Fulfilling the obligations of maintenance of land transport provided for the 9th calendar month |  | $
1.4.2.10 | Fulfilling the obligations of maintenance of land transport provided for the 10th calendar month |  | $
1.4.2.11 | Fulfilling the obligations of maintenance of land transport provided for the 11th calendar month |  | $
1.4.2.12 | Fulfilling the obligations of maintenance of land transport provided for the 12th calendar month |  | $
1.4.2.13 | Fulfilling the obligations of maintenance of land transport provided for the 13th calendar month |  | $
1.4.2.14 | Fulfilling the obligations of maintenance of land transport provided for the 14th calendar month |  | $
1.4.2.15 | Fulfilling the obligations of maintenance of land transport provided for the 15th calendar month |  | $
1.4.2.16 | Fulfilling the obligations of maintenance of land transport provided for the 16th calendar month |  | $
1.4.2.17 | Fulfilling the obligations of maintenance of land transport provided for the 17th calendar month |  | $
1.4.2.18 | Fulfilling the obligations of maintenance of land transport provided for the 18th calendar month |  | $
1.4.2.19 | Fulfilling the obligations of maintenance of land transport provided for the 19th calendar month |  | $
1.4.2.20 | Fulfilling the obligations of maintenance of land transport provided for the 20th calendar month |  | $
1.4.2.21 | Fulfilling the obligations of maintenance of land transport provided for the 21st calendar month |  | $
1.4.2.22 | Fulfilling the obligations of maintenance of land transport provided for the 22nd calendar month |  | $
1.4.2.23 | Fulfilling the obligations of maintenance of land transport provided for the 23rd calendar month |  | $
1.4.2.24 | Fulfilling the obligations of maintenance of land transport provided for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.5 | Mobile communication devices
1.5.1 | Provision of the mobile communication devices |  | $
1.5.2.1 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 1st calendar month |  | $
1.5.2.2 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 2nd calendar month |  | $
1.5.2.3 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 3rd calendar month |  | $
1.5.2.4 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 4th calendar month |  | $
1.5.2.5 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 5th calendar month |  | $
1.5.2.6 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 6th calendar month |  | $
1.5.2.7 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 7th calendar month |  | $
1.5.2.8 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 8th calendar month |  | $
1.5.2.9 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 9th calendar month |  | $
1.5.2.10 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 10th calendar month |  | $
1.5.2.11 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 11th calendar month |  | $
1.5.2.12 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 12th calendar month |  | $
1.5.2.13 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 13th calendar month |  | $
1.5.2.14 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 14th calendar month |  | $
1.5.2.15 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 15th calendar month |  | $
1.5.2.16 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 16th calendar month |  | $
1.5.2.17 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 17th calendar month |  | $
1.5.2.18 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 18th calendar month |  | $
1.5.2.19 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 19th calendar month |  | $
1.5.2.20 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 20th calendar month |  | $
1.5.2.21 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 21st calendar month |  | $
1.5.2.22 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 22nd calendar month |  | $
1.5.2.23 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 23rd calendar month |  | $
1.5.2.24 | Fulfilling the obligation of operation and maintenance of mobile communication devices for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.6 | Public Complaints and Enquiries cum Information Centre
1.6.1 | Completion of provision of 24-hour telephone hotline to receive enquiries |  | $
1.6.2.1 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 1st calendar month |  | $
1.6.2.2 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 2nd calendar month |  | $
1.6.2.3 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 3rd calendar month |  | $
1.6.2.4 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 4th calendar month |  | $
1.6.2.5 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 5th calendar month |  | $
1.6.2.6 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 6th calendar month |  | $
1.6.2.7 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 7th calendar month |  | $
1.6.2.8 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 8th calendar month |  | $
1.6.2.9 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 9th calendar month |  | $
1.6.2.10 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 10th calendar month |  | $
1.6.2.11 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 11th calendar month |  | $
1.6.2.12 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 12th calendar month |  | $
1.6.2.13 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 13th calendar month |  | $
1.6.2.14 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 14th calendar month |  | $
1.6.2.15 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 15th calendar month |  | $
1.6.2.16 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 16th calendar month |  | $
1.6.2.17 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 17th calendar month |  | $
1.6.2.18 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 18th calendar month |  | $
1.6.2.19 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 19th calendar month |  | $
1.6.2.20 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 20th calendar month |  | $
1.6.2.21 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 21st calendar month |  | $
1.6.2.22 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 22nd calendar month |  | $
1.6.2.23 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 23rd calendar month |  | $
1.6.2.24 | Fulfilling the obligations of maintenance of 24-hours telephone hotline system provided for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.7 | Survey of Site
1.7.1 | Completion of initial survey |  | $
1.7.2 | As-built survey |  | $
1.7.3 | Submission of survey report, record photos, negatives, albums and record survey |  | $
1.8 | Site Security
1.8.1 | Completion of provision of site security system |  | $
1.8.2.1 | Fulfilling the obligations of operation and maintenance of the security system for the 1st calendar month |  | $
1.8.2.2 | Fulfilling the obligations of operation and maintenance of the security system for the 2nd calendar month |  | $
1.8.2.3 | Fulfilling the obligations of operation and maintenance of the security system for the 3rd calendar month |  | $
1.8.2.4 | Fulfilling the obligations of operation and maintenance of the security system for the 4th calendar month |  | $
1.8.2.5 | Fulfilling the obligations of operation and maintenance of the security system for the 5th calendar month |  | $
1.8.2.6 | Fulfilling the obligations of operation and maintenance of the security system for the 6th calendar month |  | $
1.8.2.7 | Fulfilling the obligations of operation and maintenance of the security system for the 7th calendar month |  | $
1.8.2.8 | Fulfilling the obligations of operation and maintenance of the security system for the 8th calendar month |  | $
1.8.2.9 | Fulfilling the obligations of operation and maintenance of the security system for the 9th calendar month |  | $
1.8.2.10 | Fulfilling the obligations of operation and maintenance of the security system for the 10th calendar month |  | $
1.8.2.11 | Fulfilling the obligations of operation and maintenance of the security system for the 11th calendar month |  | $
1.8.2.12 | Fulfilling the obligations of operation and maintenance of the security system for the 12th calendar month |  | $
1.8.2.13 | Fulfilling the obligations of operation and maintenance of the security system for the 13th calendar month |  | $
1.8.2.14 | Fulfilling the obligations of operation and maintenance of the security system for the 14th calendar month |  | $
1.8.2.15 | Fulfilling the obligations of operation and maintenance of the security system for the 15th calendar month |  | $
1.8.2.16 | Fulfilling the obligations of operation and maintenance of the security system for the 16th calendar month |  | $
1.8.2.17 | Fulfilling the obligations of operation and maintenance of the security system for the 17th calendar month |  | $
1.8.2.18 | Fulfilling the obligations of operation and maintenance of the security system for the 18th calendar month |  | $
1.8.2.19 | Fulfilling the obligations of operation and maintenance of the security system for the 19th calendar month |  | $
1.8.2.20 | Fulfilling the obligations of operation and maintenance of the security system for the 20th calendar month |  | $
1.8.2.21 | Fulfilling the obligations of operation and maintenance of the security system for the 21st calendar month |  | $
1.8.2.22 | Fulfilling the obligations of operation and maintenance of the security system for the 22nd calendar month |  | $
1.8.2.23 | Fulfilling the obligations of operation and maintenance of the security system for the 23rd calendar month |  | $
1.8.2.24 | Fulfilling the obligations of operation and maintenance of the security system for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.9 | Third Party Insurance and Professional Indemnity Insurance
1.9.1 | Submission of insurance policy for Third party insurance |  | $
1.9.2 | Acceptance of insurance policy for Third party insurance |  | $
1.9.3 | Annual renewal of 2nd year for the Third party insurance |  | $
1.9.4 | Annual renewal of 3rd year for the Third party insurance |  | $
1.9.5 | Annual renewal of 4th year for the Third party insurance |  | $
1.9.6 | Annual renewal of 5th year for the Third party insurance |  | $
1.9.7 | Submission of insurance policy for Professional indemnity insurance |  | $
1.9.8 | Acceptance of insurance policy for Professional indemnity insurance |  | $
1.9.9 | Annual renewal of 2nd year for the Professional indemnity insurance |  | $
1.9.10 | Annual renewal of 3rd year for the Professional indemnity insurance |  | $
1.9.11 | Annual renewal of 4th year for the Professional indemnity insurance |  | $
1.9.12 | Annual renewal of 5th year for the Professional indemnity insurance |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.10 | Site Management Plan for Trip Ticket System
1.10.1 | Completion of site management plan for trip ticket system |  | $
1.10.2.1 | Fulfilling the obligations of implementation of trip ticket system for the 1st calendar month |  | $
1.10.2.2 | Fulfilling the obligations of implementation of trip ticket system for the 2nd calendar month |  | $
1.10.2.3 | Fulfilling the obligations of implementation of trip ticket system for the 3rd calendar month |  | $
1.10.2.4 | Fulfilling the obligations of implementation of trip ticket system for the 4th calendar month |  | $
1.10.2.5 | Fulfilling the obligations of implementation of trip ticket system for the 5th calendar month |  | $
1.10.2.6 | Fulfilling the obligations of implementation of trip ticket system for the 6th calendar month |  | $
1.10.2.7 | Fulfilling the obligations of implementation of trip ticket system for the 7th calendar month |  | $
1.10.2.8 | Fulfilling the obligations of implementation of trip ticket system for the 8th calendar month |  | $
1.10.2.9 | Fulfilling the obligations of implementation of trip ticket system for the 9th calendar month |  | $
1.10.2.10 | Fulfilling the obligations of implementation of trip ticket system for the 10th calendar month |  | $
1.10.2.11 | Fulfilling the obligations of implementation of trip ticket system for the 11th calendar month |  | $
1.10.2.12 | Fulfilling the obligations of implementation of trip ticket system for the 12th calendar month |  | $
1.10.2.13 | Fulfilling the obligations of implementation of trip ticket system for the 13th calendar month |  | $
1.10.2.14 | Fulfilling the obligations of implementation of trip ticket system for the 14th calendar month |  | $
1.10.2.15 | Fulfilling the obligations of implementation of trip ticket system for the 15th calendar month |  | $
1.10.2.16 | Fulfilling the obligations of implementation of trip ticket system for the 16th calendar month |  | $
1.10.2.17 | Fulfilling the obligations of implementation of trip ticket system for the 17th calendar month |  | $
1.10.2.18 | Fulfilling the obligations of implementation of trip ticket system for the 18th calendar month |  | $
1.10.2.19 | Fulfilling the obligations of implementation of trip ticket system for the 19th calendar month |  | $
1.10.2.20 | Fulfilling the obligations of implementation of trip ticket system for the 20th calendar month |  | $
1.10.2.21 | Fulfilling the obligations of implementation of trip ticket system for the 21st calendar month |  | $
1.10.2.22 | Fulfilling the obligations of implementation of trip ticket system for the 22nd calendar month |  | $
1.10.2.23 | Fulfilling the obligations of implementation of trip ticket system for the 23rd calendar month |  | $
1.10.2.24 | Fulfilling the obligations of implementation of trip ticket system for the 24th calendar month |  | $
1.11 | Interfacing management plan and attend co-ordination meeting
1.11.1 | Provision & update of interfacing management plan and attend co-ordination meeting for 24 months commencing from the starting date
1.11.1.1 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 1st calendar month |  | $
1.11.1.2 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 2nd calendar month |  | $
1.11.1.3 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 3rd calendar month |  | $
1.11.1.4 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 4th calendar month |  | $
1.11.1.5 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 5th calendar month |  | $
1.11.1.6 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 6th calendar month |  | $
1.11.1.7 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 7th calendar month |  | $
1.11.1.8 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 8th calendar month |  | $
1.11.1.9 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 9th calendar month |  | $
1.11.1.10 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 10th calendar month |  | $
1.11.1.11 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 11th calendar month |  | $
1.11.1.12 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 12th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.11.1.13 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 13th calendar month |  | $
1.11.1.14 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 14th calendar month |  | $
1.11.1.15 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 15th calendar month |  | $
1.11.1.16 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 16th calendar month |  | $
1.11.1.17 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 17th calendar month |  | $
1.11.1.18 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 18th calendar month |  | $
1.11.1.19 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 19th calendar month |  | $
1.11.1.20 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 20th calendar month |  | $
1.11.1.21 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 21st calendar month |  | $
1.11.1.22 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 22nd calendar month |  | $
1.11.1.23 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 23rd calendar month |  | $
1.11.1.24 | Fullfilling the obligations of provision and update of interfacing management plan and attend co-ordination meeting for the 24th calendar month |  | $
Environmental Measures
1.12 | Air Pollution Abatement
1.12.1 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 1st calendar month |  | $
1.12.2 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 2nd calendar month |  | $
1.12.3 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 3rd calendar month |  | $
1.12.4 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 4th calendar month |  | $
1.12.5 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 5th calendar month |  | $
1.12.6 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 6th calendar month |  | $
1.12.7 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 7th calendar month |  | $
1.12.8 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 8th calendar month |  | $
1.12.9 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 9th calendar month |  | $
1.12.10 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 10th calendar month |  | $
1.12.11 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 11th calendar month |  | $
1.12.12 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 12th calendar month |  | $
1.12.13 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 13th calendar month |  | $
1.12.14 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 14th calendar month |  | $
1.12.15 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 15th calendar month |  | $
1.12.16 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 16th calendar month |  | $
1.12.17 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 17th calendar month |  | $
1.12.18 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 18th calendar month |  | $
1.12.19 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 19th calendar month |  | $
1.12.20 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 20th calendar month |  | $
1.12.21 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 21st calendar month |  | $
1.12.22 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 22nd calendar month |  | $
1.12.23 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 23rd calendar month |  | $
1.12.24 | Provision, maintenance and removal of air pollution abatement measures for dusty and/or smoky activities for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.13 | Noise Pollution Abatement
1.13.1 | Provision, maintenance and removal of noise abatement practices for the 1st calendar month |  | $
1.13.2 | Provision, maintenance and removal of noise abatement practices for the 2nd calendar month |  | $
1.13.3 | Provision, maintenance and removal of noise abatement practices for the 3rd calendar month |  | $
1.13.4 | Provision, maintenance and removal of noise abatement practices for the 4th calendar month |  | $
1.13.5 | Provision, maintenance and removal of noise abatement practices for the 5th calendar month |  | $
1.13.6 | Provision, maintenance and removal of noise abatement practices for the 6th calendar month |  | $
1.13.7 | Provision, maintenance and removal of noise abatement practices for the 7th calendar month |  | $
1.13.8 | Provision, maintenance and removal of noise abatement practices for the 8th calendar month |  | $
1.13.9 | Provision, maintenance and removal of noise abatement practices for the 9th calendar month |  | $
1.13.10 | Provision, maintenance and removal of noise abatement practices for the 10th calendar month |  | $
1.13.11 | Provision, maintenance and removal of noise abatement practices for the 11th calendar month |  | $
1.13.12 | Provision, maintenance and removal of noise abatement practices for the 12th calendar month |  | $
1.13.13 | Provision, maintenance and removal of noise abatement practices for the 13th calendar month |  | $
1.13.14 | Provision, maintenance and removal of noise abatement practices for the 14th calendar month |  | $
1.13.15 | Provision, maintenance and removal of noise abatement practices for the 15th calendar month |  | $
1.13.16 | Provision, maintenance and removal of noise abatement practices for the 16th calendar month |  | $
1.13.17 | Provision, maintenance and removal of noise abatement practices for the 17th calendar month |  | $
1.13.18 | Provision, maintenance and removal of noise abatement practices for the 18th calendar month |  | $
1.13.19 | Provision, maintenance and removal of noise abatement practices for the 19th calendar month |  | $
1.13.20 | Provision, maintenance and removal of noise abatement practices for the 20th calendar month |  | $
1.13.21 | Provision, maintenance and removal of noise abatement practices for the 21st calendar month |  | $
1.13.22 | Provision, maintenance and removal of noise abatement practices for the 22nd calendar month |  | $
1.13.23 | Provision, maintenance and removal of noise abatement practices for the 23rd calendar month |  | $
1.13.24 | Provision, maintenance and removal of noise abatement practices for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.14 | Waste Management
1.14.1 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 1st calendar month |  | $
1.14.2 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 2nd calendar month |  | $
1.14.3 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 3rd calendar month |  | $
1.14.4 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 4th calendar month |  | $
1.14.5 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 5th calendar month |  | $
1.14.6 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 6th calendar month |  | $
1.14.7 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 7th calendar month |  | $
1.14.8 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 8th calendar month |  | $
1.14.9 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 9th calendar month |  | $
1.14.10 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 10th calendar month |  | $
1.14.11 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 11th calendar month |  | $
1.14.12 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 12th calendar month |  | $
1.14.13 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 13th calendar month |  | $
1.14.14 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 14th calendar month |  | $
1.14.15 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 15th calendar month |  | $
1.14.16 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 16th calendar month |  | $
1.14.17 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 17th calendar month |  | $
1.14.18 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 18th calendar month |  | $
1.14.19 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 19th calendar month |  | $
1.14.20 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 20th calendar month |  | $
1.14.21 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 21st calendar month |  | $
1.14.22 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 22nd calendar month |  | $
1.14.23 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 23rd calendar month |  | $
1.14.24 | Fulfilling the obligations of arrange and conduct on-site sorting of C&D for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.15 | Monitoring the Use of Ultra Low Sulphur Diesel (Provisional)
1.15.1 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 1st calendar month |  | $
1.15.2 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 2nd calendar month |  | $
1.15.3 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 3rd calendar month |  | $
1.15.4 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 4th calendar month |  | $
1.15.5 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 5th calendar month |  | $
1.15.6 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 6th calendar month |  | $
1.15.7 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 7th calendar month |  | $
1.15.8 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 8th calendar month |  | $
1.15.9 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 9th calendar month |  | $
1.15.10 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 10th calendar month |  | $
1.15.11 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 11th calendar month |  | $
1.15.12 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 12th calendar month |  | $
1.15.13 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 13th calendar month |  | $
1.15.14 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 14th calendar month |  | $
1.15.15 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 15th calendar month |  | $
1.15.16 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 16th calendar month |  | $
1.15.17 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 17th calendar month |  | $
1.15.18 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 18th calendar month |  | $
1.15.19 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 19th calendar month |  | $
1.15.20 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 20th calendar month |  | $
1.15.21 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 21st calendar month |  | $
1.15.22 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 22nd calendar month |  | $
1.15.23 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 23rd calendar month |  | $
1.15.24 | Fulfilling the obligations of arrange and conduct testing of fuel sample by laboratory for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.16 | Environmental Mitigation Measures
1.16.1 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 1st calendar month |  | $
1.16.2 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 2nd calendar month |  | $
1.16.3 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 3rd calendar month |  | $
1.16.4 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 4th calendar month |  | $
1.16.5 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 5th calendar month |  | $
1.16.6 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 6th calendar month |  | $
1.16.7 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 7th calendar month |  | $
1.16.8 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 8th calendar month |  | $
1.16.9 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 9th calendar month |  | $
1.16.10 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 10th calendar month |  | $
1.16.11 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 11th calendar month |  | $
1.16.12 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 12th calendar month |  | $
1.16.13 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 13th calendar month |  | $
1.16.14 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 14th calendar month |  | $
1.16.15 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 15th calendar month |  | $
1.16.16 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 16th calendar month |  | $
1.16.17 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 17th calendar month |  | $
1.16.18 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 18th calendar month |  | $
1.16.19 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 19th calendar month |  | $
1.16.20 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 20th calendar month |  | $
1.16.21 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 21st calendar month |  | $
1.16.22 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 22nd calendar month |  | $
1.16.23 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 23rd calendar month |  | $
1.16.24 | Fulfilling the obligations of provision, maintenance and removal of air related environmental mitigation measures for the 24th calendar month |  | $
1.16.25 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 1st calendar month
1.16.26 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 2nd calendar month
1.16.27 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 3rd calendar month
1.16.28 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 4th calendar month
1.16.29 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 5th calendar month
1.16.30 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 6th calendar month
1.16.31 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 7th calendar month
1.16.32 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 8th calendar month
1.16.33 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 9th calendar month
1.16.34 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 10th calendar month
1.16.35 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 11th calendar month
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
1.16.36 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 12th calendar month
1.16.37 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 13th calendar month
1.16.38 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 14th calendar month
1.16.39 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 15th calendar month
1.16.40 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 16th calendar month
1.16.41 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 17th calendar month
1.16.42 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 18th calendar month
1.16.43 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 19th calendar month
1.16.44 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 20th calendar month
1.16.45 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 21st calendar month
1.16.46 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 22nd calendar month
1.16.47 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 23rd calendar month
1.16.48 | Fulfilling the obligations of provision, maintenance and removal of noise related environmental mitigation measures |  | $
for the 24th calendar month
1.17 | Additional items required by the Contractor (to be inserted by the Contractor) |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
| Collection from Page AS.S1/1 |  | $
| Collection from Page AS.S1/2 |  | $
| Collection from Page AS.S1/3 |  | $
| Collection from Page AS.S1/4 |  | $
| Collection from Page AS.S1/5 |  | $
| Collection from Page AS.S1/6 |  | $
| Collection from Page AS.S1/7 |  | $
| Collection from Page AS.S1/8 |  | $
| Collection from Page AS.S1/9 |  | $
| Collection from Page AS.S1/10 |  | $
| Collection from Page AS.S1/11 |  | $
| Collection from Page AS.S1/12 |  | $
| Collection from Page AS.S1/13 |  | $
| Collection from Page AS.S1/14 |  | $
| Collection from Page AS.S1/15 |  | $
|  | Total Prices of Schedule No. 1 Carried to Grand Summary of the Activity Schedule | $

## A2
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2022/14
MODIFICATION WORKS OF NOISE BARRIERS ALONG YUEN LONG HIGHWAY NEAR PARK SIGNATURE
ACTIVITY SCHEDULE
Schedule No. 2 - Preservation and Protection of Trees
Item | Activity |  | Prices (HK$)
2 | Preservation and Protection of Trees
2.1 | Preservation and protection measures to the preserved trees
2.1.1 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 1st calender month |  | $
2.1.2 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 2nd calender month |  | $
2.1.3 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 3rd calender month |  | $
2.1.4 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 4th calender month |  | $
2.1.5 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 5th calender month |  | $
2.1.6 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 6th calender month |  | $
2.1.7 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 7th calender month |  | $
2.1.8 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 8th calender month |  | $
2.1.9 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 9th calender month |  | $
2.1.10 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 10th calender month |  | $
2.1.11 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 11th calender month |  | $
2.1.12 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 12th calender month |  | $
2.1.13 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 13th calender month |  | $
2.1.14 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 14th calender month |  | $
2.1.15 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 15th calender month |  | $
2.1.16 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 16th calender month |  | $
2.1.17 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 17th calender month |  | $
2.1.18 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 18th calender month |  | $
2.1.19 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 19th calender month |  | $
2.1.20 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 20th calender month |  | $
2.1.21 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 21st calender month |  | $
2.1.22 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 22nd calender month |  | $
2.1.23 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 23rd calender month |  | $
2.1.24 | Fulfilling the obligations of preservation and protection measures to the preserved trees for the 24th calender month |  | $
2.2 | Tree survey of existing trees and Report on updating of photographical records |  | $
2.3 | Tree risk assessment |  | $
2.4 | Additional items required by the Contractor (to be inserted by the Contractor) |  | $
|  | Total Prices of Schedule No. 2 Carried to Grand Summary of the Activity Schedule | $
Item | Activity |  | Prices (HK$)
| Collection from Page AS.S4/1 |  | $
|  | Total Prices of Schedule No. 4 Carried to Grand Summary of the Activity Schedule | $

## A3
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2022/14
MODIFICATION WORKS OF NOISE BARRIERS ALONG YUEN LONG HIGHWAY NEAR PARK SIGNATURE
ACTIVITY SCHEDULE
Schedule No. 3 - Modification Works of Noise Barriers
Item | Activity |  | Prices (HK$)
3 | Modification Works of Noise Barriers
3.1 | Dismantling and disposal of existing steel posts, sub-frames, base plates and other accessories of noise barriers
3.1.1 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay A1
3.1.2 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay B1
3.1.3 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay B2
3.1.4 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay B3
3.1.5 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay B4
3.1.6 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay B5
3.1.7 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay C1
3.1.8 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay C2
3.1.9 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay C3
3.1.10 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay C4
3.1.11 | Completion of dismantling and disposal of existing vertical posts, sub-frames, base plates and other accessories |  | $
of noise barriers for Bay C5
3.2 | Installation of new vertical posts and base plates of noise barriers
3.2.1 | Completion of installation of new vertical posts and base plates of noise barriers for Bay A1 |  | $
3.2.2 | Completion of installation of new vertical posts and base plates of noise barriers for Bay B1 |  | $
3.2.3 | Completion of installation of new vertical posts and base plates of noise barriers for Bay B2 |  | $
3.2.4 | Completion of installation of new vertical posts and base plates of noise barriers for Bay B3 |  | $
3.2.5 | Completion of installation of new vertical posts and base plates of noise barriers for Bay B4 |  | $
3.2.6 | Completion of installation of new vertical posts and base plates of noise barriers for Bay B5 |  | $
3.2.7 | Completion of installation of new vertical posts and base plates of noise barriers for Bay C1 |  | $
3.2.8 | Completion of installation of new vertical posts and base plates of noise barriers for Bay C2 |  | $
3.2.9 | Completion of installation of new vertical posts and base plates of noise barriers for Bay C3 |  | $
3.2.10 | Completion of installation of new vertical posts and base plates of noise barriers for Bay C4 |  | $
3.2.11 | Completion of installation of new vertical posts and base plates of noise barriers for Bay C5 |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
3.3 | Dismantling, storing and re-erecting of existing noise barrier panels
3.3.1 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay A1 |  | $
3.3.2 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay B1 |  | $
3.3.3 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay B2 |  | $
3.3.4 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay B3 |  | $
3.3.5 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay B4 |  | $
3.3.6 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay B5 |  | $
3.3.7 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay C1 |  | $
3.3.8 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay C2 |  | $
3.3.9 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay C3 |  | $
3.3.10 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay C4 |  | $
3.3.11 | Completion of dismantling, storing and re-erecting of existing noise barrier panels for Bay C5 |  | $
3.4 | Installation of new sub-frames and other accessories of noise barriers
3.4.1 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay A1 |  | $
3.4.2 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay B1 |  | $
3.4.3 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay B2 |  | $
3.4.4 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay B3 |  | $
3.4.5 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay B4 |  | $
3.4.6 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay B5 |  | $
3.4.7 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay C1 |  | $
3.4.8 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay C2 |  | $
3.4.9 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay C3 |  | $
3.4.10 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay C4 |  | $
3.4.11 | Completion of installation of new sub-frames and other accessories of noise barriers for Bay C5 |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
3.5 | Installation of new panels of noise barriers
3.5.1 | Completion of installation of new panels of noise barriers for Bay A1 |  | $
3.5.2 | Completion of installation of new panels of noise barriers for Bay B1 |  | $
3.5.3 | Completion of installation of new panels of noise barriers for Bay B2 |  | $
3.5.4 | Completion of installation of new panels of noise barriers for Bay B3 |  | $
3.5.5 | Completion of installation of new panels of noise barriers for Bay B4 |  | $
3.5.6 | Completion of installation of new panels of noise barriers for Bay B5 |  | $
3.5.7 | Completion of installation of new panels of noise barriers for Bay C1 |  | $
3.5.8 | Completion of installation of new panels of noise barriers for Bay C2 |  | $
3.5.9 | Completion of installation of new panels of noise barriers for Bay C3 |  | $
3.5.10 | Completion of installation of new panels of noise barriers for Bay C4 |  | $
3.5.11 | Completion of installation of new panels of noise barriers for Bay C5 |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
3.6 | Contractor's Design for Noise Barriers Bay A1, Bay B1 to B5 and Bay C1 to C5
3.6.1 | Submission of Contractor's Design and Check Certificates on noise barrier panels, sub-frames and other accessories |  | $
for the full compliance with Specification and Drawings of the Contract with Project Manager's approval
3.7 | Spare Parts
3.7.1 | Provision of additional PMMA panels as specified in PS Clause 27.19 |  | $
3.7.2 | Provision of additional polycarbonate panels as specified in PS Clause 27.19 |  | $
3.7.3 | Provision of additional stainless steel hexagon nuts with washers as specified in PS Clause 27.19 |  | $
3.8 | Miscellanous
3.8.1 | Submission of As-constructed Drawings |  | $
3.8.2 | Submission of Operation and Maintenance Manuals |  | $
3.9 | Additional items required by the Contractor (to be inserted by the Contractor) |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
| Collection from Page AS.S3/1 |  | $
| Collection from Page AS.S3/2 |  | $
| Collection from Page AS.S3/3 |  | $
| Collection from Page AS.S3/4 |  | $
|  | Total Prices of Schedule No. 3 Carried to Grand Summary of the Activity Schedule | $

## A4
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2022/14
MODIFICATION WORKS OF NOISE BARRIERS ALONG YUEN LONG HIGHWAY NEAR PARK SIGNATURE
ACTIVITY SCHEDULE
Schedule No. 4 - Monitoring Payment of Wages
Item | Activity |  | Prices (HK$)
4 | Monitoring Payment of Wages
4.1 | Completion of establishment monitoring system for payment of wages |  | $
4.2.1 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 1st calendar month |  | $ | 9000
4.2.2 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 2nd calendar month |  | $ | 9000
4.2.3 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 3rd calendar month |  | $ | 9000
4.2.4 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 4th calendar month |  | $ | 9000
4.2.5 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 5th calendar month |  | $ | 9000
4.2.6 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 6th calendar month |  | $ | 9000
4.2.7 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 7th calendar month |  | $ | 9000
4.2.8 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 8th calendar month |  | $ | 9000
4.2.9 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 9th calendar month |  | $ | 9000
4.2.10 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 10th calendar month |  | $ | 9000
4.2.11 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 11th calendar month |  | $ | 9000
4.2.12 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 12th calendar month |  | $ | 9000
4.2.13 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 13th calendar month |  | $ | 9000
4.2.14 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 14th calendar month |  | $ | 9000
4.2.15 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 15th calendar month |  | $ | 9000
4.2.16 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 16th calendar month |  | $ | 9000
4.2.17 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 17th calendar month |  | $ | 9000
4.2.18 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 18th calendar month |  | $ | 9000
4.2.19 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 19th calendar month |  | $ | 9000
4.2.20 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 20th calendar month |  | $ | 9000
4.2.21 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 21st calendar month |  | $ | 9000
4.2.22 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 22nd calendar month |  | $ | 9000
4.2.23 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 23rd calendar month |  | $ | 9000
4.2.24 | Fulfilling the obligations of operating the monitoring system of payment of wages for the 24th calendar month |  | $ | 9000
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
4.3 | Contractor's Labour Officer
4.3.1 | Provision of Contractor's Labour Officer for the 1st calendar month |  | $
4.3.2 | Provision of Contractor's Labour Officer for the 2nd calendar month |  | $
4.3.3 | Provision of Contractor's Labour Officer for the 3rd calendar month |  | $
4.3.4 | Provision of Contractor's Labour Officer for the 4th calendar month |  | $
4.3.5 | Provision of Contractor's Labour Officer for the 5th calendar month |  | $
4.3.6 | Provision of Contractor's Labour Officer for the 6th calendar month |  | $
4.3.7 | Provision of Contractor's Labour Officer for the 7th calendar month |  | $
4.3.8 | Provision of Contractor's Labour Officer for the 8th calendar month |  | $
4.3.9 | Provision of Contractor's Labour Officer for the 9th calendar month |  | $
4.3.10 | Provision of Contractor's Labour Officer for the 10th calendar month |  | $
4.3.11 | Provision of Contractor's Labour Officer for the 11th calendar month |  | $
4.3.12 | Provision of Contractor's Labour Officer for the 12th calendar month |  | $
4.3.13 | Provision of Contractor's Labour Officer for the 13th calendar month |  | $
4.3.14 | Provision of Contractor's Labour Officer for the 14th calendar month |  | $
4.3.15 | Provision of Contractor's Labour Officer for the 15th calendar month |  | $
4.3.16 | Provision of Contractor's Labour Officer for the 16th calendar month |  | $
4.3.17 | Provision of Contractor's Labour Officer for the 17th calendar month |  | $
4.3.18 | Provision of Contractor's Labour Officer for the 18th calendar month |  | $
4.3.19 | Provision of Contractor's Labour Officer for the 19th calendar month |  | $
4.3.20 | Provision of Contractor's Labour Officer for the 20th calendar month |  | $
4.3.21 | Provision of Contractor's Labour Officer for the 21st calendar month |  | $
4.3.22 | Provision of Contractor's Labour Officer for the 22nd calendar month |  | $
4.3.23 | Provision of Contractor's Labour Officer for the 23rd calendar month |  | $
4.3.24 | Provision of Contractor's Labour Officer for the 24th calendar month |  | $
|  | Total carried to collection | $
Item | Activity |  | Prices (HK$)
| Collection from Page AS.S4/1 |  | $
| Collection from Page AS.S4/2 |  | $
|  | Total Prices of Schedule No. 4 Carried to Grand Summary of the Activity Schedule | $

## A5
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2022/14
MODIFICATION WORKS OF NOISE BARRIERS ALONG YUEN LONG HIGHWAY NEAR PARK SIGNATURE
ACTIVITY SCHEDULE
Schedule No. 5 - Site Safety
Item | Activity |  | Prices (HK$)
5 | Site Safety
5.1.1 | Provide Safety Officer for the 1st calendar month |  | $ | 1800
5.1.2 | Provide Safety Officer for the 2nd calendar month |  | $ | 1800
5.1.3 | Provide Safety Officer for the 3rd calendar month |  | $ | 1800
5.1.4 | Provide Safety Officer for the 4th calendar month |  | $ | 1800
5.1.5 | Provide Safety Officer for the 5th calendar month |  | $ | 1800
5.1.6 | Provide Safety Officer for the 6th calendar month |  | $ | 1800
5.1.7 | Provide Safety Officer for the 7th calendar month |  | $ | 1800
5.1.8 | Provide Safety Officer for the 8th calendar month |  | $ | 1800
5.1.9 | Provide Safety Officer for the 9th calendar month |  | $ | 1800
5.1.10 | Provide Safety Officer for the 10th calendar month |  | $ | 1800
5.1.11 | Provide Safety Officer for the 11th calendar month |  | $ | 1800
5.1.12 | Provide Safety Officer for the 12th calendar month |  | $ | 1800
5.1.13 | Provide Safety Officer for the 13th calendar month |  | $ | 1800
5.1.14 | Provide Safety Officer for the 14th calendar month |  | $ | 1800
5.1.15 | Provide Safety Officer for the 15th calendar month |  | $ | 1800
5.1.16 | Provide Safety Officer for the 16th calendar month |  | $ | 1800
5.1.17 | Provide Safety Officer for the 17th calendar month |  | $ | 1800
5.1.18 | Provide Safety Officer for the 18th calendar month |  | $ | 1800
5.1.19 | Provide Safety Officer for the 19th calendar month |  | $ | 1800
5.1.20 | Provide Safety Officer for the 20th calendar month |  | $ | 1800
5.1.21 | Provide Safety Officer for the 21st calendar month |  | $ | 1800
5.1.22 | Provide Safety Officer for the 22nd calendar month |  | $ | 1800
5.1.23 | Provide Safety Officer for the 23rd calendar month |  | $ | 1800
5.1.24 | Provide Safety Officer for the 24th calendar month |  | $ | 1800
|  | Total carried to collection | $ | 43200
Item | Activity |  | Prices (HK$)
5.2.1 | Attend Site Safety Meeting Committee for the 1st calendar month |  | $ | 445
5.2.2 | Attend Site Safety Meeting Committee for the 2nd calendar month |  | $ | 445
5.2.3 | Attend Site Safety Meeting Committee for the 3rd calendar month |  | $ | 445
5.2.4 | Attend Site Safety Meeting Committee for the 4th calendar month |  | $ | 445
5.2.5 | Attend Site Safety Meeting Committee for the 5th calendar month |  | $ | 445
5.2.6 | Attend Site Safety Meeting Committee for the 6th calendar month |  | $ | 445
5.2.7 | Attend Site Safety Meeting Committee for the 7th calendar month |  | $ | 445
5.2.8 | Attend Site Safety Meeting Committee for the 8th calendar month |  | $ | 445
5.2.9 | Attend Site Safety Meeting Committee for the 9th calendar month |  | $ | 445
5.2.10 | Attend Site Safety Meeting Committee for the 10th calendar month |  | $ | 445
5.2.11 | Attend Site Safety Meeting Committee for the 11th calendar month |  | $ | 445
5.2.12 | Attend Site Safety Meeting Committee for the 12th calendar month |  | $ | 445
5.2.13 | Attend Site Safety Meeting Committee for the 13th calendar month |  | $ | 445
5.2.14 | Attend Site Safety Meeting Committee for the 14th calendar month |  | $ | 445
5.2.15 | Attend Site Safety Meeting Committee for the 15th calendar month |  | $ | 445
5.2.16 | Attend Site Safety Meeting Committee for the 16th calendar month |  | $ | 445
5.2.17 | Attend Site Safety Meeting Committee for the 17th calendar month |  | $ | 445
5.2.18 | Attend Site Safety Meeting Committee for the 18th calendar month |  | $ | 445
5.2.19 | Attend Site Safety Meeting Committee for the 19th calendar month |  | $ | 445
5.2.20 | Attend Site Safety Meeting Committee for the 20th calendar month |  | $ | 445
5.2.21 | Attend Site Safety Meeting Committee for the 21st calendar month |  | $ | 445
5.2.22 | Attend Site Safety Meeting Committee for the 22nd calendar month |  | $ | 445
5.2.23 | Attend Site Safety Meeting Committee for the 23rd calendar month |  | $ | 445
5.2.24 | Attend Site Safety Meeting Committee for the 24th calendar month |  | $ | 445
|  | Total carried to collection | $ | 10680
Item | Activity |  | Prices (HK$)
5.3.1 | Attend Site Safety Committee for the 1st calendar month |  | $ | 445
5.3.2 | Attend Site Safety Committee for the 2nd calendar month |  | $ | 445
5.3.3 | Attend Site Safety Committee for the 3rd calendar month |  | $ | 445
5.3.4 | Attend Site Safety Committee for the 4th calendar month |  | $ | 445
5.3.5 | Attend Site Safety Committee for the 5th calendar month |  | $ | 445
5.3.6 | Attend Site Safety Committee for the 6th calendar month |  | $ | 445
5.3.7 | Attend Site Safety Committee for the 7th calendar month |  | $ | 445
5.3.8 | Attend Site Safety Committee for the 8th calendar month |  | $ | 445
5.3.9 | Attend Site Safety Committee for the 9th calendar month |  | $ | 445
5.3.10 | Attend Site Safety Committee for the 10th calendar month |  | $ | 445
5.3.11 | Attend Site Safety Committee for the 11th calendar month |  | $ | 445
5.3.12 | Attend Site Safety Committee for the 12th calendar month |  | $ | 445
5.3.13 | Attend Site Safety Committee for the 13th calendar month |  | $ | 445
5.3.14 | Attend Site Safety Committee for the 14th calendar month |  | $ | 445
5.3.15 | Attend Site Safety Committee for the 15th calendar month |  | $ | 445
5.3.16 | Attend Site Safety Committee for the 16th calendar month |  | $ | 445
5.3.17 | Attend Site Safety Committee for the 17th calendar month |  | $ | 445
5.3.18 | Attend Site Safety Committee for the 18th calendar month |  | $ | 445
5.3.19 | Attend Site Safety Committee for the 19th calendar month |  | $ | 445
5.3.20 | Attend Site Safety Committee for the 20th calendar month |  | $ | 445
5.3.21 | Attend Site Safety Committee for the 21st calendar month |  | $ | 445
5.3.22 | Attend Site Safety Committee for the 22nd calendar month |  | $ | 445
5.3.23 | Attend Site Safety Committee for the 23d calendar month |  | $ | 445
5.3.24 | Attend Site Safety Committee for the 24th calendar month |  | $ | 445
|  | Total carried to collection | $ | 10680
Item | Activity |  | Prices (HK$)
5.4.1 | Arrange and attend weekly safety walk for the 1st calendar month |  | $ | 1340
5.4.2 | Arrange and attend weekly safety walk for the 2nd calendar month |  | $ | 1340
5.4.3 | Arrange and attend weekly safety walk for the 3rd calendar month |  | $ | 1340
5.4.4 | Arrange and attend weekly safety walk for the 4th calendar month |  | $ | 1340
5.4.5 | Arrange and attend weekly safety walk for the 5th calendar month |  | $ | 1340
5.4.6 | Arrange and attend weekly safety walk for the 6th calendar month |  | $ | 1340
5.4.7 | Arrange and attend weekly safety walk for the 7th calendar month |  | $ | 1340
5.4.8 | Arrange and attend weekly safety walk for the 8th calendar month |  | $ | 1340
5.4.9 | Arrange and attend weekly safety walk for the 9th calendar month |  | $ | 1340
5.4.10 | Arrange and attend weekly safety walk for the 10th calendar month |  | $ | 1340
5.4.11 | Arrange and attend weekly safety walk for the 11th calendar month |  | $ | 1340
5.4.12 | Arrange and attend weekly safety walk for the 12th calendar month |  | $ | 1340
5.4.13 | Arrange and attend weekly safety walk for the 13th calendar month |  | $ | 1340
5.4.14 | Arrange and attend weekly safety walk for the 14th calendar month |  | $ | 1340
5.4.15 | Arrange and attend weekly safety walk for the 15th calendar month |  | $ | 1340
5.4.16 | Arrange and attend weekly safety walk for the 16th calendar month |  | $ | 1340
5.4.17 | Arrange and attend weekly safety walk for the 17th calendar month |  | $ | 1340
5.4.18 | Arrange and attend weekly safety walk for the 18th calendar month |  | $ | 1340
5.4.19 | Arrange and attend weekly safety walk for the 19th calendar month |  | $ | 1340
5.4.20 | Arrange and attend weekly safety walk for the 20th calendar month |  | $ | 1340
5.4.21 | Arrange and attend weekly safety walk for the 21st calendar month |  | $ | 1340
5.4.22 | Arrange and attend weekly safety walk for the 22nd calendar month |  | $ | 1340
5.4.23 | Arrange and attend weekly safety walk for the 23d calendar month |  | $ | 1340
5.4.24 | Arrange and attend weekly safety walk for the 24th calendar month |  | $ | 1340
|  | Total carried to collection | $ | 32160
Item | Activity |  | Prices (HK$)
5.5 | Provide safety training in the form of safety training for specified trade workers
5.5.1.1 | 1st One day course |  | $ | 600
5.5.1.2 | 2nd One day course |  | $ | 600
5.5.1.3 | 3rd One day course |  | $ | 600
5.5.1.4 | 4th One day course |  | $ | 600
5.5.1.5 | 5th One day course |  | $ | 600
5.5.1.6 | 6th One day course |  | $ | 600
5.5.1.7 | 7th One day course |  | $ | 600
5.5.1.8 | 8th One day course |  | $ | 600
5.5.1.9 | 9th One day course |  | $ | 600
5.5.1.10 | 10th One day course |  | $ | 600
5.5.1.11 | 11th One day course |  | $ | 600
5.5.1.12 | 12th One day course |  | $ | 600
5.5.1.13 | 13th One day course |  | $ | 600
5.5.1.14 | 14th One day course |  | $ | 600
5.5.1.15 | 15th One day course |  | $ | 600
5.5.1.16 | 16th One day course |  | $ | 600
5.5.1.17 | 17th One day course |  | $ | 600
5.5.1.18 | 18th One day course |  | $ | 600
5.5.2.1 | 1st Half day validation course |  | $ | 350
5.5.2.2 | 2nd Half day validation course |  | $ | 350
5.5.2.3 | 3rd Half day validation course |  | $ | 350
5.5.2.4 | 4th Half day validation course |  | $ | 350
5.5.2.5 | 5th Half day validation course |  | $ | 350
5.5.2.6 | 6th Half day validation course |  | $ | 350
5.5.2.7 | 7th Half day validation course |  | $ | 350
5.5.2.8 | 8th Half day validation course |  | $ | 350
5.5.2.9 | 9th Half day validation course |  | $ | 350
5.5.2.10 | 10th Half day validation course |  | $ | 350
5.5.2.11 | 11th Half day validation course |  | $ | 350
5.5.2.12 | 12th Half day validation course |  | $ | 350
5.5.2.13 | 13th Half day validation course |  | $ | 350
5.5.2.14 | 14th Half day validation course |  | $ | 350
5.5.2.15 | 15th Half day validation course |  | $ | 350
5.5.2.16 | 16th Half day validation course |  | $ | 350
5.5.2.17 | 17th Half day validation course |  | $ | 350
5.5.2.18 | 18th Half day validation course |  | $ | 350
|  | Total carried to collection |  | 17100
5.6.1 | Provide safety training in the form of site specific induction training for the 1st calendar month |  | $ | 450
5.6.2 | Provide safety training in the form of site specific induction training for the 2nd calendar month |  | $ | 450
5.6.3 | Provide safety training in the form of site specific induction training for the 3rd calendar month |  | $ | 450
5.6.4 | Provide safety training in the form of site specific induction training for the 4th calendar month |  | $ | 450
5.6.5 | Provide safety training in the form of site specific induction training for the 5th calendar month |  | $ | 450
5.6.6 | Provide safety training in the form of site specific induction training for the 6th calendar month |  | $ | 450
5.6.7 | Provide safety training in the form of site specific induction training for the 7th calendar month |  | $ | 450
5.6.8 | Provide safety training in the form of site specific induction training for the 8th calendar month |  | $ | 450
5.6.9 | Provide safety training in the form of site specific induction training for the 9th calendar month |  | $ | 450
5.6.10 | Provide safety training in the form of site specific induction training for the 10th calendar month |  | $ | 450
5.6.11 | Provide safety training in the form of site specific induction training for the 11th calendar month |  | $ | 450
5.6.12 | Provide safety training in the form of site specific induction training for the 12th calendar month |  | $ | 450
5.6.13 | Provide safety training in the form of site specific induction training for the 13th calendar month |  | $ | 450
5.6.14 | Provide safety training in the form of site specific induction training for the 14th calendar month |  | $ | 450
5.6.15 | Provide safety training in the form of site specific induction training for the 15th calendar month |  | $ | 450
5.6.16 | Provide safety training in the form of site specific induction training for the 16th calendar month |  | $ | 450
5.6.17 | Provide safety training in the form of site specific induction training for the 17th calendar month |  | $ | 450
5.6.18 | Provide safety training in the form of site specific induction training for the 18th calendar month |  | $ | 450
5.6.19 | Provide safety training in the form of site specific induction training for the 19th calendar month |  | $ | 450
5.6.20 | Provide safety training in the form of site specific induction training for the 20th calendar month |  | $ | 450
5.6.21 | Provide safety training in the form of site specific induction training for the 21th calendar month |  | $ | 450
5.6.22 | Provide safety training in the form of site specific induction training for the 22th calendar month |  | $ | 450
5.6.23 | Provide safety training in the form of site specific induction training for the 23th calendar month |  | $ | 450
5.6.24 | Provide safety training in the form of site specific induction training for the 24th calendar month |  | $ | 450
|  | Total carried to collection | $ | 10800
Item | Activity |  | Prices (HK$)
5.7.1 | Provide safety training in the form of tool-box talks for the 1st calendar month |  | $ | 900
5.7.2 | Provide safety training in the form of tool-box talks for the 2nd calendar month |  | $ | 900
5.7.3 | Provide safety training in the form of tool-box talks for the 3rd calendar month |  | $ | 900
5.7.4 | Provide safety training in the form of tool-box talks for the 4th calendar month |  | $ | 900
5.7.5 | Provide safety training in the form of tool-box talks for the 5th calendar month |  | $ | 900
5.7.6 | Provide safety training in the form of tool-box talks for the 6th calendar month |  | $ | 900
5.7.7 | Provide safety training in the form of tool-box talks for the 7th calendar month |  | $ | 900
5.7.8 | Provide safety training in the form of tool-box talks for the 8th calendar month |  | $ | 900
5.7.9 | Provide safety training in the form of tool-box talks for the 9th calendar month |  | $ | 900
5.7.10 | Provide safety training in the form of tool-box talks for the 10th calendar month |  | $ | 900
5.7.11 | Provide safety training in the form of tool-box talks for the 11th calendar month |  | $ | 900
5.7.12 | Provide safety training in the form of tool-box talks for the 12th calendar month |  | $ | 900
5.7.13 | Provide safety training in the form of tool-box talks for the 13th calendar month |  | $ | 900
5.7.14 | Provide safety training in the form of tool-box talks for the 14th calendar month |  | $ | 900
5.7.15 | Provide safety training in the form of tool-box talks for the 15th calendar month |  | $ | 900
5.7.16 | Provide safety training in the form of tool-box talks for the 16th calendar month |  | $ | 900
5.7.17 | Provide safety training in the form of tool-box talks for the 17th calendar month |  | $ | 900
5.7.18 | Provide safety training in the form of tool-box talks for the 18th calendar month |  | $ | 900
5.7.19 | Provide safety training in the form of tool-box talks for the 19th calendar month |  | $ | 900
5.7.20 | Provide safety training in the form of tool-box talks for the 20th calendar month |  | $ | 900
5.7.21 | Provide safety training in the form of tool-box talks for the 21st calendar month |  | $ | 900
5.7.22 | Provide safety training in the form of tool-box talks for the 22nd calendar month |  | $ | 900
5.7.23 | Provide safety training in the form of tool-box talks for the 23rd calendar month |  | $ | 900
5.7.24 | Provide safety training in the form of tool-box talks for the 24th calendar month |  | $ | 900
|  | Total carried to collection | $ | 21600
Item | Activity |  | Prices (HK$)
5.8 | Participate in safety promotional campaign as instructed by the Project Manager
5.8.1 | Fulfilling the obligation of participate in safety promotional campaign for the 1st safety promotional campaign |  | $ | 530
5.8.2 | Fulfilling the obligation of participate in safety promotional campaign for the 2nd safety promotional campaign |  | $ | 530
5.8.3 | Fulfilling the obligation of participate in safety promotional campaign for the 3rd safety promotional campaign |  | $ | 530
5.8.4 | Fulfilling the obligation of participate in safety promotional campaign for the 4th safety promotional campaign |  | $ | 530
5.8.5 | Fulfilling the obligation of participate in safety promotional campaign for the 5th safety promotional campaign |  | $ | 530
5.8.6 | Fulfilling the obligation of participate in safety promotional campaign for the 6th safety promotional campaign |  | $ | 530
5.8.7 | Fulfilling the obligation of participate in safety promotional campaign for the 7th safety promotional campaign |  | $ | 530
5.8.8 | Fulfilling the obligation of participate in safety promotional campaign for the 8th safety promotional campaign |  | $ | 530
5.8.9 | Fulfilling the obligation of participate in safety promotional campaign for the 9th safety promotional campaign |  | $ | 530
5.8.10 | Fulfilling the obligation of participate in safety promotional campaign for the 10th safety promotional campaign |  | $ | 530
5.8.11 | Fulfilling the obligation of participate in safety promotional campaign for the 11th safety promotional campaign |  | $ | 530
5.8.12 | Fulfilling the obligation of participate in safety promotional campaign for the 12th safety promotional campaign |  | $ | 530
|  | Total carried to collection | $ | 6360
Item | Activity |  | Prices (HK$)
5.9.1 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 1st calendar month |  | $ | 3800
5.9.2 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 2nd calendar month |  | $ | 3800
5.9.3 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 3rd calendar month |  | $ | 3800
5.9.4 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 4th calendar month |  | $ | 3800
5.9.5 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 5th calendar month |  | $ | 3800
5.9.6 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 6th calendar month |  | $ | 3800
5.9.7 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 7th calendar month |  | $ | 3800
5.9.8 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 8th calendar month |  | $ | 3800
5.9.9 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 9th calendar month |  | $ | 3800
5.9.10 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 10th calendar month |  | $ | 3800
5.9.11 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 11th calendar month |  | $ | 3800
5.9.12 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 12th calendar month |  | $ | 3800
5.9.13 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 13th calendar month |  | $ | 3800
5.9.14 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 14th calendar month |  | $ | 3800
5.9.15 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 15th calendar month |  | $ | 3800
5.9.16 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 16th calendar month |  | $ | 3800
5.9.17 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 17th calendar month |  | $ | 3800
5.9.18 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 18th calendar month |  | $ | 3800
5.9.19 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 19th calendar month |  | $ | 3800
5.9.20 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 20th calendar month |  | $ | 3800
5.9.21 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 21st calendar month |  | $ | 3800
5.9.22 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 22nd calendar month |  | $ | 3800
5.9.23 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 23rd calendar month |  | $ | 3800
5.9.24 | Arrangement and hold pre-work Activities of Site Safety Cycle for the 24th calendar month |  | $ | 3800
5.10.1 | Prevention of heat stroke at work in a hot environment for the 1st calendar month between May 2023 and October 2023 |  | $ | 1500
5.10.2 | Prevention of heat stroke at work in a hot environment for the 2nd calendar month between May 2023 and October 2023 |  | $ | 1500
5.10.3 | Prevention of heat stroke at work in a hot environment for the 3rd calendar month between May 2023 and October 2023 |  | $ | 1500
5.10.4 | Prevention of heat stroke at work in a hot environment for the 4th calendar month between May 2023 and October 2023 |  | $ | 1500
5.10.5 | Prevention of heat stroke at work in a hot environment for the 5th calendar month between May 2023 and October 2023 |  | $ | 1500
5.10.6 | Prevention of heat stroke at work in a hot environment for the 6th calendar month between May 2023 and October 2023 |  | $ | 1500
|  | Total carried to collection | $ | 100200
Item | Activity |  | Prices (HK$)
| Collection from Page AS.S5/1 |  | $ | 43200
| Collection from Page AS.S5/2 |  | $ | 10680
| Collection from Page AS.S5/3 |  | $ | 10680
| Collection from Page AS.S5/4 |  | $ | 32160
| Collection from Page AS.S5/5 |  | $ | 17100
| Collection from Page AS.S5/6 |  | $ | 10800
| Collection from Page AS.S5/7 |  | $ | 21600
| Collection from Page AS.S5/8 |  | $ | 6360
| Collection from Page AS.S5/9 |  | $ | 100200
|  | Total Prices of Schedule No. 5 Carried to Grand Summary of the Activity Schedule | $ | 252780
[BLANK PAGE]

## A6
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2022/14
MODIFICATION WORKS OF NOISE BARRIERS ALONG YUEN LONG HIGHWAY NEAR PARK SIGNATURE
ACTIVITY SCHEDULE
Schedule No. 6 - Site Cleanliness and Tidiness
Item | Activity |  | Prices (HK$)
6 | Site Cleanliness and Tidiness
6.1.1 | Completion of daily cleaning for the 1st calendar month |  | $ | 20333
6.1.2 | Completion of daily cleaning for the 2nd calendar month |  | $ | 20333
6.1.3 | Completion of daily cleaning for the 3rd calendar month |  | $ | 20333
6.1.4 | Completion of daily cleaning for the 4th calendar month |  | $ | 20333
6.1.5 | Completion of daily cleaning for the 5th calendar month |  | $ | 20333
6.1.6 | Completion of daily cleaning for the 6th calendar month |  | $ | 20333
6.1.7 | Completion of daily cleaning for the 7th calendar month |  | $ | 20333
6.1.8 | Completion of daily cleaning for the 8th calendar month |  | $ | 20333
6.1.9 | Completion of daily cleaning for the 9th calendar month |  | $ | 20333
6.1.10 | Completion of daily cleaning for the 10th calendar month |  | $ | 20333
6.1.11 | Completion of daily cleaning for the 11th calendar month |  | $ | 20333
6.1.12 | Completion of daily cleaning for the 12th calendar month |  | $ | 20333
6.1.13 | Completion of daily cleaning for the 13th calendar month |  | $ | 20333
6.1.14 | Completion of daily cleaning for the 14th calendar month |  | $ | 20333
6.1.15 | Completion of daily cleaning for the 15th calendar month |  | $ | 20333
6.1.16 | Completion of daily cleaning for the 16th calendar month |  | $ | 20333
6.1.17 | Completion of daily cleaning for the 17th-24th calendar months |  | $ | 20333
|  | Total carried to collection | $ | 345661
Item | Activity |  | Prices (HK$)
6.2.1 | Completion of weekly tidying for the 1st calendar month |  | $ | 4333
6.2.2 | Completion of weekly tidying for the 2nd calendar month |  | $ | 4333
6.2.3 | Completion of weekly tidying for the 3rd calendar month |  | $ | 4333
6.2.4 | Completion of weekly tidying for the 4th calendar month |  | $ | 4333
6.2.5 | Completion of weekly tidying for the 5th calendar month |  | $ | 4333
6.2.6 | Completion of weekly tidying for the 6th calendar month |  | $ | 4333
6.2.7 | Completion of weekly tidying for the 7th calendar month |  | $ | 4333
6.2.8 | Completion of weekly tidying for the 8th calendar month |  | $ | 4333
6.2.9 | Completion of weekly tidying for the 9th calendar month |  | $ | 4333
6.2.10 | Completion of weekly tidying for the 10th calendar month |  | $ | 4333
6.2.11 | Completion of weekly tidying for the 11th calendar month |  | $ | 4333
6.2.12 | Completion of weekly tidying for the 12th calendar month |  | $ | 4333
6.2.13 | Completion of weekly tidying for the 13th calendar month |  | $ | 4333
6.2.14 | Completion of weekly tidying for the 14th calendar month |  | $ | 4333
6.2.15 | Completion of weekly tidying for the 15th calendar month |  | $ | 4333
6.2.16 | Completion of weekly tidying for the 16th calendar month |  | $ | 4333
6.2.17 | Completion of weekly tidying for the 17th-24th calendar months |  | $ | 4333
|  | Total carried to collection | $ | 73661
Item | Activity |  | Prices (HK$)
| Collection from Page AS.S6/1 |  | $ | 345661
| Collection from Page AS.S6/2 |  | $ | 73661
|  | Total Prices of Schedule No. 6 Carried to Grand Summary of the Activity Schedule | $ | 419322

## A13 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 13 - Noise Barriers NB09
Item | Activity |  |  | Prices (HK$)
13 | Noise Barriers NB09
13.1 | Piling Works
13.1.1 | Establishment of piling plant |  |  | $
13.1.2 | Pre-drilling works |  |  | $
13.1.3 | Piling
13.1.3.1 | Excavation of piles
13.1.3.1.1 | Completion of excavation of piles for Bay NB09-01P |  |  | $
13.1.3.1.2 | Completion of excavation of piles for Bay NB09-02P |  |  | $
13.1.3.1.3 | Completion of excavation of piles for Bay NB09-03P |  |  | $
13.1.3.1.4 | Completion of excavation of piles for Bay NB09-04P |  |  | $
13.1.3.2 | Installation of reinforcement for piles
13.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB09-01P |  |  | $
13.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB09-02P |  |  | $
13.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB09-03P |  |  | $
13.1.3.2.4 | Completion of installation of reinforcement of piles for Bay NB09-04P |  |  | $
13.1.3.3 | Completion of piling works
13.1.3.3.1 | Completion of all piling works for Bay NB09-01P |  |  | $
13.1.3.3.2 | Completion of all piling works for Bay NB09-02P |  |  | $
13.1.3.3.3 | Completion of all piling works for Bay NB09-03P |  |  | $
13.1.3.3.4 | Completion of all piling works for Bay NB09-04P |  |  | $
13.1.4 | Pile tests
13.1.4.1 | Completion of all pile tests |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
13.2 | Substructure
13.2.1 | Excavation for pile cap
13.2.1.1 | Completion of excavation of pile cap for Bay NB09-01P |  |  | $
13.2.1.2 | Completion of excavation of pile cap for Bay NB09-02P |  |  | $
13.2.1.3 | Completion of excavation of pile cap for Bay NB09-03P |  |  | $
13.2.1.4 | Completion of excavation of pile cap for Bay NB09-04P |  |  | $
13.2.2 | Fixing of reinforcement
13.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB09-01P |  |  | $
13.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB09-02P |  |  | $
13.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB09-03P |  |  | $
13.2.2.4 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB09-04P |  |  | $
13.2.3 | Completion of pile caps with stem wall
13.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB09-01P |  |  | $
13.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB09-02P |  |  | $
13.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB09-03P |  |  | $
13.2.3.4 | Completion of all pile caps with stem wall and movement joints for Bay NB09-04P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
13.3 | Superstructure
13.3.1 | Installation of vertical posts for noise barriers
13.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB09-01P |  |  | $
13.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB09-02P |  |  | $
13.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB09-03P |  |  | $
13.3.1.4 | Completion of installation of vertical posts of noise barriers for Bay NB09-04P |  |  | $
13.3.2 | Installation of tie beams for noise barriers
13.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB09-01P |  |  | $
13.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB09-02P |  |  | $
13.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB09-03P |  |  | $
13.3.2.4 | Completion of installation of tie bems of noise barriers for Bay NB09-04P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
13.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
13.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB09 (Bay NB09-01P to 04P) |  | $
13.4.2 |  | Photovoltaic (PV) System for Noise Barrier NB09 |  | $
13.5 | Miscellanous
13.5.1 | Completion of installation of drainage |  |  | $
13.5.2 | Completion of installation of watermains |  |  | $
13.5.3 | Completion of diversion of existing utilities |  |  | $
13.5.4 | Completion of reinstatement of existing footpath |  |  | $
13.5.5 | Completion of reinstatement of carriageway |  |  | $
13.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S13/1 |  |  | $
| Collection from Page AS.S13/2 |  |  | $
| Collection from Page AS.S13/3 |  |  | $
| Collection from Page AS.S13/4 |  |  | $
|  |  | Total Prices of Schedule No. 13 Carried to Grand Summary of the Activity Schedule | $

## A14 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 14 - Noise Barriers NB10
Item | Activity |  |  | Prices (HK$)
14 | Noise Barriers NB10
14.1 | Piling Works
14.1.1 | Establishment of piling plant |  |  | $
14.1.2 | Pre-drilling works |  |  | $
14.1.3 | Piling
14.1.3.1 | Excavation of piles
14.1.3.1.1 | Completion of excavation of piles for Bay NB10-01P |  |  | $
14.1.3.1.2 | Completion of excavation of piles for Bay NB10-02P |  |  | $
14.1.3.1.3 | Completion of excavation of piles for Bay NB10-03P |  |  | $
14.1.3.1.4 | Completion of excavation of piles for Bay NB10-04P |  |  | $
14.1.3.2 | Installation of reinforcement for piles
14.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB10-01P |  |  | $
14.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB10-02P |  |  | $
14.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB10-03P |  |  | $
14.1.3.2.4 | Completion of installation of reinforcement of piles for Bay NB10-04P |  |  | $
14.1.3.3 | Completion of piling works
14.1.3.3.1 | Completion of all piling works for Bay NB10-01P |  |  | $
14.1.3.3.2 | Completion of all piling works for Bay NB10-02P |  |  | $
14.1.3.3.3 | Completion of all piling works for Bay NB10-03P |  |  | $
14.1.3.3.4 | Completion of all piling works for Bay NB10-04P |  |  | $
14.1.4 | Preliminary Pile
14.1.4.1 | Completion of one preliminary pile |  |  | $
14.1.4.2 | Completion of all pile tests for preliminary pile |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
14.2 | Substructure
14.2.1 | Excavation for pile cap
14.2.1.1 | Completion of excavation of pile cap for Bay NB10-01P |  |  | $
14.2.1.2 | Completion of excavation of pile cap for Bay NB10-02P |  |  | $
14.2.1.3 | Completion of excavation of pile cap for Bay NB10-03P |  |  | $
14.2.1.4 | Completion of excavation of pile cap for Bay NB10-04P |  |  | $
14.2.2 | Fixing of reinforcement
14.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB10-01P |  |  | $
14.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB10-02P |  |  | $
14.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB10-03P |  |  | $
14.2.2.4 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB10-04P |  |  | $
14.2.3 | Completion of pile caps with stem wall
14.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB10-01P |  |  | $
14.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB10-02P |  |  | $
14.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB10-03P |  |  | $
14.2.3.4 | Completion of all pile caps with stem wall and movement joints for Bay NB10-04P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
14.3 | Superstructure
14.3.1 | Installation of vertical posts for noise barriers
14.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB10-01P |  |  | $
14.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB10-02P |  |  | $
14.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB10-03P |  |  | $
14.3.1.4 | Completion of installation of vertical posts of noise barriers for Bay NB10-04P |  |  | $
14.3.2 | Installation of tie beams for noise barriers
14.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB10-01P |  |  | $
14.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB10-02P |  |  | $
14.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB10-03P |  |  | $
14.3.2.4 | Completion of installation of tie bems of noise barriers for Bay NB10-04P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
14.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
14.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB10 (Bay NB10-01P to 04P) |  | $
14.4.2 |  | Photovoltaic (PV) System for Noise Barrier NB10 |  | $
14.5 | Miscellanous
14.5.1 | Completion of installation of drainage |  |  | $
14.5.2 | Completion of installation of watermains |  |  | $
14.5.3 | Completion of diversion of existing utilities |  |  | $
14.5.4 | Completion of reinstatement of existing footpath |  |  | $
14.5.5 | Completion of reinstatement of carriageway |  |  | $
14.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S14/1 |  |  | $
| Collection from Page AS.S14/2 |  |  | $
| Collection from Page AS.S14/3 |  |  | $
| Collection from Page AS.S14/4 |  |  | $
|  |  | Total Prices of Schedule No. 14 Carried to Grand Summary of the Activity Schedule | $

## A15 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 15 - Noise Barriers NB11
Item | Activity |  |  | Prices (HK$)
15 | Noise Barriers NB11
15.1 | Piling Works
15.1.1 | Establishment of piling plant |  |  | $
15.1.2 | Pre-drilling works |  |  | $
15.1.3 | Piling
15.1.3.1 | Excavation of piles
15.1.3.1.1 | Completion of excavation of piles for Bay NB11-01P |  |  | $
15.1.3.1.2 | Completion of excavation of piles for Bay NB11-02P |  |  | $
15.1.3.1.3 | Completion of excavation of piles for Bay NB11-03P |  |  | $
15.1.3.1.4 | Completion of excavation of piles for Bay NB11-04P |  |  | $
15.1.3.1.5 | Completion of excavation of piles for Bay NB11-05P |  |  | $
15.1.3.2 | Installation of reinforcement for piles
15.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB11-01P |  |  | $
15.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB11-02P |  |  | $
15.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB11-03P |  |  | $
15.1.3.2.4 | Completion of installation of reinforcement of piles for Bay NB11-04P |  |  | $
15.1.3.2.5 | Completion of installation of reinforcement of piles for Bay NB11-05P |  |  | $
15.1.3.3 | Completion of piling works
15.1.3.3.1 | Completion of all piling works for Bay NB11-01P |  |  | $
15.1.3.3.2 | Completion of all piling works for Bay NB11-02P |  |  | $
15.1.3.3.3 | Completion of all piling works for Bay NB11-03P |  |  | $
15.1.3.3.4 | Completion of all piling works for Bay NB11-04P |  |  | $
15.1.3.3.5 | Completion of all piling works for Bay NB11-05P |  |  | $
15.1.4 | Preliminary Pile
15.1.4.1 | Completion of one preliminary pile |  |  | $
15.1.4.2 | Completion of all pile tests for preliminary pile |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
15.2 | Substructure
15.2.1 | Excavation for pile cap
15.2.1.1 | Completion of excavation of pile cap for Bay NB11-01P |  |  | $
15.2.1.2 | Completion of excavation of pile cap for Bay NB11-02P |  |  | $
15.2.1.3 | Completion of excavation of pile cap for Bay NB11-03P |  |  | $
15.2.1.4 | Completion of excavation of pile cap for Bay NB11-04P |  |  | $
15.2.1.5 | Completion of excavation of pile cap for Bay NB11-05P |  |  | $
15.2.2 | Fixing of reinforcement
15.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB11-01P |  |  | $
15.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB11-02P |  |  | $
15.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB11-03P |  |  | $
15.2.2.4 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB11-04P |  |  | $
15.2.2.5 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB11-05P |  |  | $
15.2.3 | Completion of pile caps with stem wall
15.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB11-01P |  |  | $
15.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB11-02P |  |  | $
15.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB11-03P |  |  | $
15.2.3.4 | Completion of all pile caps with stem wall and movement joints for Bay NB11-04P |  |  | $
15.2.3.5 | Completion of all pile caps with stem wall and movement joints for Bay NB11-05P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
15.3 | Superstructure
15.3.1 | Installation of vertical posts for noise barriers
15.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB11-01P |  |  | $
15.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB11-02P |  |  | $
15.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB11-03P |  |  | $
15.3.1.4 | Completion of installation of vertical posts of noise barriers for Bay NB11-04P |  |  | $
15.3.1.5 | Completion of installation of vertical posts of noise barriers for Bay NB11-05P |  |  | $
15.3.2 | Installation of tie beams for noise barriers
15.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB11-01P |  |  | $
15.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB11-02P |  |  | $
15.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB11-03P |  |  | $
15.3.2.4 | Completion of installation of tie bems of noise barriers for Bay NB11-04P |  |  | $
15.3.2.5 | Completion of installation of tie bems of noise barriers for Bay NB11-05P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
15.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
15.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB11 (Bay NB11-01P to 05P) |  | $
15.5 | Miscellanous
15.5.1 | Completion of installation of drainage |  |  | $
15.5.2 | Completion of installation of watermains |  |  | $
15.5.3 | Completion of diversion of existing utilities |  |  | $
15.5.4 | Completion of reinstatement of existing footpath |  |  | $
15.5.5 | Completion of reinstatement of carriageway |  |  | $
15.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S15/1 |  |  | $
| Collection from Page AS.S15/2 |  |  | $
| Collection from Page AS.S15/3 |  |  | $
| Collection from Page AS.S15/4 |  |  | $
|  |  | Total Prices of Schedule No. 15 Carried to Grand Summary of the Activity Schedule | $

## A16 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 16 - Noise Barriers NB12
Item | Activity |  |  | Prices (HK$)
16 | Noise Barriers NB12
16.1 | Piling Works
16.1.1 | Establishment of piling plant |  |  | $
16.1.2 | Pre-drilling works |  |  | $
16.1.3 | Piling
16.1.3.1 | Excavation of piles
16.1.3.1.1 | Completion of excavation of piles for Bay NB12-01P |  |  | $
16.1.3.1.2 | Completion of excavation of piles for Bay NB12-02P |  |  | $
16.1.3.1.3 | Completion of excavation of piles for Bay NB12-03P |  |  | $
16.1.3.2 | Installation of reinforcement for piles
16.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB12-01P |  |  | $
16.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB12-02P |  |  | $
16.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB12-03P |  |  | $
16.1.3.3 | Completion of piling works
16.1.3.3.1 | Completion of all piling works for Bay NB12-01P |  |  | $
16.1.3.3.2 | Completion of all piling works for Bay NB12-02P |  |  | $
16.1.3.3.3 | Completion of all piling works for Bay NB12-03P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
16.2 | Substructure
16.2.1 | Excavation for pile cap
16.2.1.1 | Completion of excavation of pile cap for Bay NB12-01P |  |  | $
16.2.1.2 | Completion of excavation of pile cap for Bay NB12-02P |  |  | $
16.2.1.3 | Completion of excavation of pile cap for Bay NB12-03P |  |  | $
16.2.2 | Fixing of reinforcement
16.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB12-01P |  |  | $
16.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB12-02P |  |  | $
16.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB12-03P |  |  | $
16.2.3 | Completion of pile caps with stem wall
16.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB12-01P |  |  | $
16.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB12-02P |  |  | $
16.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB12-03P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
16.3 | Superstructure
16.3.1 | Installation of vertical posts for noise barriers
16.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB12-01P |  |  | $
16.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB12-02P |  |  | $
16.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB12-03P |  |  | $
16.3.2 | Installation of tie beams for noise barriers
16.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB12-01P |  |  | $
16.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB12-02P |  |  | $
16.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB12-03P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
16.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
16.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB12 (Bay NB12-01P to 03P) |  | $
16.5 | Miscellanous
16.5.1 | Completion of installation of drainage |  |  | $
16.5.2 | Completion of installation of watermains |  |  | $
16.5.3 | Completion of diversion of existing utilities |  |  | $
16.5.4 | Completion of reinstatement of existing footpath |  |  | $
16.5.5 | Completion of reinstatement of carriageway |  |  | $
16.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S16/1 |  |  | $
| Collection from Page AS.S16/2 |  |  | $
| Collection from Page AS.S16/3 |  |  | $
| Collection from Page AS.S16/4 |  |  | $
|  |  | Total Prices of Schedule No. 16 Carried to Grand Summary of the Activity Schedule | $

## A17 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 17 - Noise Barriers NB13
Item | Activity |  |  | Prices (HK$)
17 | Noise Barriers NB13
17.1 | Piling Works
17.1.1 | Establishment of piling plant |  |  | $
17.1.2 | Pre-drilling works |  |  | $
17.1.3 | Piling
17.1.3.1 | Excavation of piles
17.1.3.1.1 | Completion of excavation of piles for Bay NB13-01P |  |  | $
17.1.3.1.2 | Completion of excavation of piles for Bay NB13-02P |  |  | $
17.1.3.1.3 | Completion of excavation of piles for Bay NB13-03P |  |  | $
17.1.3.2 | Installation of reinforcement for piles
17.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB13-01P |  |  | $
17.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB13-02P |  |  | $
17.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB13-03P |  |  | $
17.1.3.3 | Completion of piling works
17.1.3.3.1 | Completion of all piling works for Bay NB13-01P |  |  | $
17.1.3.3.2 | Completion of all piling works for Bay NB13-02P |  |  | $
17.1.3.3.3 | Completion of all piling works for Bay NB13-03P |  |  | $
17.1.4 | Preliminary Pile
17.1.4.1 | Completion of one preliminary pile |  |  | $
17.1.4.2 | Completion of all pile tests for preliminary pile |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
17.2 | Substructure
17.2.1 | Excavation for pile cap
17.2.1.1 | Completion of excavation of pile cap for Bay NB13-01P |  |  | $
17.2.1.2 | Completion of excavation of pile cap for Bay NB13-02P |  |  | $
17.2.1.3 | Completion of excavation of pile cap for Bay NB13-03P |  |  | $
17.2.2 | Fixing of reinforcement
17.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB13-01P |  |  | $
17.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB13-02P |  |  | $
17.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB13-03P |  |  | $
17.2.3 | Completion of pile caps with stem wall
17.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB13-01P |  |  | $
17.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB13-02P |  |  | $
17.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB13-03P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
17.3 | Superstructure
17.3.1 | Installation of vertical posts for noise barriers
17.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB13-01P |  |  | $
17.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB13-02P |  |  | $
17.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB13-03P |  |  | $
17.3.2 | Installation of tie beams for noise barriers
17.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB13-01P |  |  | $
17.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB13-02P |  |  | $
17.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB13-03P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
17.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
17.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB13 (Bay NB13-01P to 03P) |  | $
17.5 | Miscellanous
17.5.1 | Completion of installation of drainage |  |  | $
17.5.2 | Completion of installation of watermains |  |  | $
17.5.3 | Completion of diversion of existing utilities |  |  | $
17.5.4 | Completion of reinstatement of existing footpath |  |  | $
17.5.5 | Completion of reinstatement of carriageway |  |  | $
17.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S17/1 |  |  | $
| Collection from Page AS.S17/2 |  |  | $
| Collection from Page AS.S17/3 |  |  | $
| Collection from Page AS.S17/4 |  |  | $
$
|  |  | Total Prices of Schedule No. 17 Carried to Grand Summary of the Activity Schedule | $

## A18 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 18 - Noise Barriers NB14
Item | Activity |  |  | Prices (HK$)
18 | Noise Barriers NB14
18.1 | Piling Works
18.1.1 | Establishment of piling plant |  |  | $
18.1.2 | Pre-drilling works |  |  | $
18.1.3 | Piling
18.1.3.1 | Excavation of piles
18.1.3.1.1 | Completion of excavation of piles for Bay NB14-01P |  |  | $
18.1.3.1.2 | Completion of excavation of piles for Bay NB14-02P |  |  | $
18.1.3.1.3 | Completion of excavation of piles for Bay NB14-03P |  |  | $
18.1.3.1.4 | Completion of excavation of piles for Bay NB14-04P |  |  | $
18.1.3.2 | Installation of reinforcement for piles
18.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB14-01P |  |  | $
18.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB14-02P |  |  | $
18.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB14-03P |  |  | $
18.1.3.2.4 | Completion of installation of reinforcement of piles for Bay NB14-04P |  |  | $
18.1.3.3 | Completion of piling works
18.1.3.3.1 | Completion of all piling works for Bay NB14-01P |  |  | $
18.1.3.3.2 | Completion of all piling works for Bay NB14-02P |  |  | $
18.1.3.3.3 | Completion of all piling works for Bay NB14-03P |  |  | $
18.1.3.3.4 | Completion of all piling works for Bay NB14-04P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
18.2 | Substructure
18.2.1 | Excavation for pile cap
18.2.1.1 | Completion of excavation of pile cap for Bay NB14-01P |  |  | $
18.2.1.2 | Completion of excavation of pile cap for Bay NB14-02P |  |  | $
18.2.1.3 | Completion of excavation of pile cap for Bay NB14-03P |  |  | $
18.2.1.4 | Completion of excavation of pile cap for Bay NB14-04P |  |  | $
18.2.2 | Fixing of reinforcement
18.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB14-01P |  |  | $
18.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB14-02P |  |  | $
18.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB14-03P |  |  | $
18.2.2.4 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB14-04P |  |  | $
18.2.3 | Completion of pile caps with stem wall
18.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB14-01P |  |  | $
18.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB14-02P |  |  | $
18.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB14-03P |  |  | $
18.2.3.4 | Completion of all pile caps with stem wall and movement joints for Bay NB14-04P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
18.3 | Superstructure
18.3.1 | Installation of vertical posts for noise barriers
18.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB14-01P |  |  | $
18.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB14-02P |  |  | $
18.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB14-03P |  |  | $
18.3.1.4 | Completion of installation of vertical posts of noise barriers for Bay NB14-04P |  |  | $
18.3.2 | Installation of tie beams for noise barriers
18.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB14-01P |  |  | $
18.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB14-02P |  |  | $
18.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB14-03P |  |  | $
18.3.2.4 | Completion of installation of tie bems of noise barriers for Bay NB14-04P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
18.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
18.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB14 (Bay NB14-01P to 04P) |  | $
18.5 | Miscellanous
18.5.1 | Completion of installation of drainage |  |  | $
18.5.2 | Completion of installation of watermains |  |  | $
18.5.3 | Completion of diversion of existing utilities |  |  | $
18.5.4 | Completion of reinstatement of existing footpath |  |  | $
18.5.5 | Completion of reinstatement of carriageway |  |  | $
18.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S18/1 |  |  | $
| Collection from Page AS.S18/2 |  |  | $
| Collection from Page AS.S18/3 |  |  | $
| Collection from Page AS.S18/4 |  |  | $
|  |  | Total Prices of Schedule No. 18 Carried to Grand Summary of the Activity Schedule | $

## A19 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 19 - Noise Barriers NB15
Item | Activity |  |  | Prices (HK$)
19 | Noise Barriers NB15
19.1 | Piling Works
19.1.1 | Establishment of piling plant |  |  | $
19.1.2 | Pre-drilling works |  |  | $
19.1.3 | Piling
19.1.3.1 | Excavation of piles
19.1.3.1.1 | Completion of excavation of piles for Bay NB15-01P |  |  | $
19.1.3.1.2 | Completion of excavation of piles for Bay NB15-02P |  |  | $
19.1.3.1.3 | Completion of excavation of piles for Bay NB15-03P |  |  | $
19.1.3.1.4 | Completion of excavation of piles for Bay NB15-04P |  |  | $
19.1.3.1.5 | Completion of excavation of piles for Bay NB15-05P |  |  | $
19.1.3.2 | Installation of reinforcement for piles
19.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB15-01P |  |  | $
19.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB15-02P |  |  | $
19.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB15-03P |  |  | $
19.1.3.2.4 | Completion of installation of reinforcement of piles for Bay NB15-04P |  |  | $
19.1.3.2.5 | Completion of installation of reinforcement of piles for Bay NB15-05P |  |  | $
19.1.3.3 | Completion of piling works
19.1.3.3.1 | Completion of all piling works for Bay NB15-01P |  |  | $
19.1.3.3.2 | Completion of all piling works for Bay NB15-02P |  |  | $
19.1.3.3.3 | Completion of all piling works for Bay NB15-03P |  |  | $
19.1.3.3.4 | Completion of all piling works for Bay NB15-04P |  |  | $
19.1.3.3.5 | Completion of all piling works for Bay NB15-05P |  |  | $
19.1.4 | Pile tests
19.1.4.1 | Completion of all pile tests |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
19.2 | Substructure
19.2.1 | Excavation for pile cap
19.2.1.1 | Completion of excavation of pile cap for Bay NB15-01P |  |  | $
19.2.1.2 | Completion of excavation of pile cap for Bay NB15-02P |  |  | $
19.2.1.3 | Completion of excavation of pile cap for Bay NB15-03P |  |  | $
19.2.1.4 | Completion of excavation of pile cap for Bay NB15-04P |  |  | $
19.2.1.5 | Completion of excavation of pile cap for Bay NB15-05P |  |  | $
19.2.2 | Fixing of reinforcement
19.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB15-01P |  |  | $
19.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB15-02P |  |  | $
19.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB15-03P |  |  | $
19.2.2.4 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB15-04P |  |  | $
19.2.2.5 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB15-05P |  |  | $
19.2.3 | Completion of pile caps with stem wall
19.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB15-01P |  |  | $
19.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB15-02P |  |  | $
19.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB15-03P |  |  | $
19.2.3.4 | Completion of all pile caps with stem wall and movement joints for Bay NB15-04P |  |  | $
19.2.3.5 | Completion of all pile caps with stem wall and movement joints for Bay NB15-05P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
19.3 | Superstructure
19.3.1 | Installation of vertical posts for noise barriers
19.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB15-01P |  |  | $
19.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB15-02P |  |  | $
19.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB15-03P |  |  | $
19.3.1.4 | Completion of installation of vertical posts of noise barriers for Bay NB15-04P |  |  | $
19.3.1.5 | Completion of installation of vertical posts of noise barriers for Bay NB15-05P |  |  | $
19.3.2 | Installation of tie beams for noise barriers
19.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB15-01P |  |  | $
19.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB15-02P |  |  | $
19.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB15-03P |  |  | $
19.3.2.4 | Completion of installation of tie bems of noise barriers for Bay NB15-04P |  |  | $
19.3.2.5 | Completion of installation of tie bems of noise barriers for Bay NB15-05P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
19.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
19.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB15 (Bay NB15-01P to 05P) |  | $
19.5 | Miscellanous
19.5.1 | Completion of installation of drainage |  |  | $
19.5.2 | Completion of installation of watermains |  |  | $
19.5.3 | Completion of diversion of existing utilities |  |  | $
19.5.4 | Completion of reinstatement of existing footpath |  |  | $
19.5.5 | Completion of reinstatement of carriageway |  |  | $
19.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S19/1 |  |  | $
| Collection from Page AS.S19/2 |  |  | $
| Collection from Page AS.S19/3 |  |  | $
| Collection from Page AS.S19/4 |  |  | $
$
|  |  | Total Prices of Schedule No. 19 Carried to Grand Summary of the Activity Schedule | $

## A20 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 20 - Noise Barriers NB16
Item | Activity |  |  | Prices (HK$)
20 | Noise Barriers NB16
20.1 | Piling Works
20.1.1 | Establishment of piling plant |  |  | $
20.1.2 | Pre-drilling works |  |  | $
20.1.3 | Piling
20.1.3.1 | Excavation of piles
20.1.3.1.1 | Completion of excavation of piles for Bay NB16-01P |  |  | $
20.1.3.1.2 | Completion of excavation of piles for Bay NB16-02P |  |  | $
20.1.3.1.3 | Completion of excavation of piles for Bay NB16-03P |  |  | $
20.1.3.1.4 | Completion of excavation of piles for Bay NB16-04P |  |  | $
20.1.3.1.5 | Completion of excavation of piles for Bay NB16-05P |  |  | $
20.1.3.1.6 | Completion of excavation of piles for Bay NB16-06P |  |  | $
20.1.3.1.7 | Completion of excavation of piles for Bay NB16-07P |  |  | $
20.1.3.1.8 | Completion of excavation of piles for Bay NB16-08P |  |  | $
20.1.3.1.9 | Completion of excavation of piles for Bay NB16-09P |  |  | $
20.1.3.1.10 | Completion of excavation of piles for Bay NB16-10P |  |  | $
20.1.3.1.11 | Completion of excavation of piles for Bay NB16-11P |  |  | $
20.1.3.1.12 | Completion of excavation of piles for Bay NB16-12P |  |  | $
20.1.3.1.13 | Completion of excavation of piles for Bay NB16-13P |  |  | $
20.1.3.1.14 | Completion of excavation of piles for Bay NB16-14P |  |  | $
20.1.3.1.15 | Completion of excavation of piles for Bay NB16-15P |  |  | $
20.1.3.1.16 | Completion of excavation of piles for Bay NB16-16P |  |  | $
20.1.3.1.17 | Completion of excavation of piles for Bay NB16-17P |  |  | $
20.1.3.1.18 | Completion of excavation of piles for Bay NB16-18P |  |  | $
20.1.3.1.19 | Completion of excavation of piles for Bay NB16-19P |  |  | $
20.1.3.1.20 | Completion of excavation of piles for Bay NB16-20P |  |  | $
20.1.3.1.21 | Completion of excavation of piles for Bay NB16-21P |  |  | $
20.1.3.1.22 | Completion of excavation of piles for Bay NB16-22P |  |  | $
20.1.3.2 | Installation of reinforcement for piles
20.1.3.2.1 | Completion of installation of reinforcement of piles for Bay NB16-01P |  |  | $
20.1.3.2.2 | Completion of installation of reinforcement of piles for Bay NB16-02P |  |  | $
20.1.3.2.3 | Completion of installation of reinforcement of piles for Bay NB16-03P |  |  | $
20.1.3.2.4 | Completion of installation of reinforcement of piles for Bay NB16-04P |  |  | $
20.1.3.2.5 | Completion of installation of reinforcement of piles for Bay NB16-05P |  |  | $
20.1.3.2.6 | Completion of installation of reinforcement of piles for Bay NB16-06P |  |  | $
20.1.3.2.7 | Completion of installation of reinforcement of piles for Bay NB16-07P |  |  | $
20.1.3.2.8 | Completion of installation of reinforcement of piles for Bay NB16-08P |  |  | $
20.1.3.2.9 | Completion of installation of reinforcement of piles for Bay NB16-09P |  |  | $
20.1.3.2.10 | Completion of installation of reinforcement of piles for Bay NB16-10P |  |  | $
20.1.3.2.11 | Completion of installation of reinforcement of piles for Bay NB16-11P |  |  | $
20.1.3.2.12 | Completion of installation of reinforcement of piles for Bay NB16-12P |  |  | $
20.1.3.2.13 | Completion of installation of reinforcement of piles for Bay NB16-13P |  |  | $
20.1.3.2.14 | Completion of installation of reinforcement of piles for Bay NB16-14P |  |  | $
20.1.3.2.15 | Completion of installation of reinforcement of piles for Bay NB16-15P |  |  | $
20.1.3.2.16 | Completion of installation of reinforcement of piles for Bay NB16-16P |  |  | $
20.1.3.2.17 | Completion of installation of reinforcement of piles for Bay NB16-17P |  |  | $
20.1.3.2.18 | Completion of installation of reinforcement of piles for Bay NB16-18P |  |  | $
20.1.3.2.19 | Completion of installation of reinforcement of piles for Bay NB16-19P |  |  | $
20.1.3.2.20 | Completion of installation of reinforcement of piles for Bay NB16-20P |  |  | $
20.1.3.2.21 | Completion of installation of reinforcement of piles for Bay NB16-21P |  |  | $
20.1.3.2.22 | Completion of installation of reinforcement of piles for Bay NB16-22P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
20.1.3.3 | Completion of piling works
20.1.3.3.1 | Completion of all piling works for Bay NB16-01P |  |  | $
20.1.3.3.2 | Completion of all piling works for Bay NB16-02P |  |  | $
20.1.3.3.3 | Completion of all piling works for Bay NB16-03P |  |  | $
20.1.3.3.4 | Completion of all piling works for Bay NB16-04P |  |  | $
20.1.3.3.5 | Completion of all piling works for Bay NB16-05P |  |  | $
20.1.3.3.6 | Completion of all piling works for Bay NB16-06P |  |  | $
20.1.3.3.7 | Completion of all piling works for Bay NB16-07P |  |  | $
20.1.3.3.8 | Completion of all piling works for Bay NB16-08P |  |  | $
20.1.3.3.9 | Completion of all piling works for Bay NB16-09P |  |  | $
20.1.3.3.10 | Completion of all piling works for Bay NB16-10P |  |  | $
20.1.3.3.11 | Completion of all piling works for Bay NB16-11P |  |  | $
20.1.3.3.12 | Completion of all piling works for Bay NB16-12P |  |  | $
20.1.3.3.13 | Completion of all piling works for Bay NB16-13P |  |  | $
20.1.3.3.14 | Completion of all piling works for Bay NB16-14P |  |  | $
20.1.3.3.15 | Completion of all piling works for Bay NB16-15P |  |  | $
20.1.3.3.16 | Completion of all piling works for Bay NB16-16P |  |  | $
20.1.3.3.17 | Completion of all piling works for Bay NB16-17P |  |  | $
20.1.3.3.18 | Completion of all piling works for Bay NB16-18P |  |  | $
20.1.3.3.19 | Completion of all piling works for Bay NB16-19P |  |  | $
20.1.3.3.20 | Completion of all piling works for Bay NB16-20P |  |  | $
20.1.3.3.21 | Completion of all piling works for Bay NB16-21P |  |  | $
20.1.3.3.22 | Completion of all piling works for Bay NB16-22P |  |  | $
20.1.4 | Pile tests
20.1.4.1 | Completion of all pile tests |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
20.2 | Substructure
20.2.1 | Excavation for pile cap
20.2.1.1 | Completion of excavation of pile cap for Bay NB16-01P |  |  | $
20.2.1.2 | Completion of excavation of pile cap for Bay NB16-02P |  |  | $
20.2.1.3 | Completion of excavation of pile cap for Bay NB16-03P |  |  | $
20.2.1.4 | Completion of excavation of pile cap for Bay NB16-04P |  |  | $
20.2.1.5 | Completion of excavation of pile cap for Bay NB16-05P |  |  | $
20.2.1.6 | Completion of excavation of pile cap for Bay NB16-06P |  |  | $
20.2.1.7 | Completion of excavation of pile cap for Bay NB16-07P |  |  | $
20.2.1.8 | Completion of excavation of pile cap for Bay NB16-08P |  |  | $
20.2.1.9 | Completion of excavation of pile cap for Bay NB16-09P |  |  | $
20.2.1.10 | Completion of excavation of pile cap for Bay NB16-10P |  |  | $
20.2.1.11 | Completion of excavation of pile cap for Bay NB16-11P |  |  | $
20.2.1.12 | Completion of excavation of pile cap for Bay NB16-12P |  |  | $
20.2.1.13 | Completion of excavation of pile cap for Bay NB16-13P |  |  | $
20.2.1.14 | Completion of excavation of pile cap for Bay NB16-14P |  |  | $
20.2.1.15 | Completion of excavation of pile cap for Bay NB16-15P |  |  | $
20.2.1.16 | Completion of excavation of pile cap for Bay NB16-16P |  |  | $
20.2.1.17 | Completion of excavation of pile cap for Bay NB16-17P |  |  | $
20.2.1.18 | Completion of excavation of pile cap for Bay NB16-18P |  |  | $
20.2.1.19 | Completion of excavation of pile cap for Bay NB16-19P |  |  | $
20.2.1.20 | Completion of excavation of pile cap for Bay NB16-20P |  |  | $
20.2.1.21 | Completion of excavation of pile cap for Bay NB16-21P |  |  | $
20.2.1.22 | Completion of excavation of pile cap for Bay NB16-22P |  |  | $
20.2.2 | Fixing of reinforcement
20.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-01P |  |  | $
20.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-02P |  |  | $
20.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-03P |  |  | $
20.2.2.4 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-04P |  |  | $
20.2.2.5 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-05P |  |  | $
20.2.2.6 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-06P |  |  | $
20.2.2.7 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-07P |  |  | $
20.2.2.8 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-08P |  |  | $
20.2.2.9 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-09P |  |  | $
20.2.2.10 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-10P |  |  | $
20.2.2.11 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-11P |  |  | $
20.2.2.12 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-12P |  |  | $
20.2.2.13 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-13P |  |  | $
20.2.2.14 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-14P |  |  | $
20.2.2.15 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-15P |  |  | $
20.2.2.16 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-16P |  |  | $
20.2.2.17 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-17P |  |  | $
20.2.2.18 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-18P |  |  | $
20.2.2.19 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-19P |  |  | $
20.2.2.20 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-20P |  |  | $
20.2.2.21 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-21P |  |  | $
20.2.2.22 | Completion of fixing of reinforcement of pile cap and stem wall for Bay NB16-22P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
20.2.3 | Completion of pile caps with stem wall
20.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay NB16-01P |  |  | $
20.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay NB16-02P |  |  | $
20.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay NB16-03P |  |  | $
20.2.3.4 | Completion of all pile caps with stem wall and movement joints for Bay NB16-04P |  |  | $
20.2.3.5 | Completion of all pile caps with stem wall and movement joints for Bay NB16-05P |  |  | $
20.2.3.6 | Completion of all pile caps with stem wall and movement joints for Bay NB16-06P |  |  | $
20.2.3.7 | Completion of all pile caps with stem wall and movement joints for Bay NB16-07P |  |  | $
20.2.3.8 | Completion of all pile caps with stem wall and movement joints for Bay NB16-08P |  |  | $
20.2.3.9 | Completion of all pile caps with stem wall and movement joints for Bay NB16-09P |  |  | $
20.2.3.10 | Completion of all pile caps with stem wall and movement joints for Bay NB16-10P |  |  | $
20.2.3.11 | Completion of all pile caps with stem wall and movement joints for Bay NB16-11P |  |  | $
20.2.3.12 | Completion of all pile caps with stem wall and movement joints for Bay NB16-12P |  |  | $
20.2.3.13 | Completion of all pile caps with stem wall and movement joints for Bay NB16-13P |  |  | $
20.2.3.14 | Completion of all pile caps with stem wall and movement joints for Bay NB16-14P |  |  | $
20.2.3.15 | Completion of all pile caps with stem wall and movement joints for Bay NB16-15P |  |  | $
20.2.3.16 | Completion of all pile caps with stem wall and movement joints for Bay NB16-16P |  |  | $
20.2.3.17 | Completion of all pile caps with stem wall and movement joints for Bay NB16-17P |  |  | $
20.2.3.18 | Completion of all pile caps with stem wall and movement joints for Bay NB16-18P |  |  | $
20.2.3.19 | Completion of all pile caps with stem wall and movement joints for Bay NB16-19P |  |  | $
20.2.3.20 | Completion of all pile caps with stem wall and movement joints for Bay NB16-20P |  |  | $
20.2.3.21 | Completion of all pile caps with stem wall and movement joints for Bay NB16-21P |  |  | $
20.2.3.22 | Completion of all pile caps with stem wall and movement joints for Bay NB16-22P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
20.3 | Superstructure
20.3.1 | Installation of vertical posts for noise barriers
20.3.1.1 | Completion of installation of vertical posts of noise barriers for Bay NB16-01P |  |  | $
20.3.1.2 | Completion of installation of vertical posts of noise barriers for Bay NB16-02P |  |  | $
20.3.1.3 | Completion of installation of vertical posts of noise barriers for Bay NB16-03P |  |  | $
20.3.1.4 | Completion of installation of vertical posts of noise barriers for Bay NB16-04P |  |  | $
20.3.1.5 | Completion of installation of vertical posts of noise barriers for Bay NB16-05P |  |  | $
20.3.1.6 | Completion of installation of vertical posts of noise barriers for Bay NB16-06P |  |  | $
20.3.1.7 | Completion of installation of vertical posts of noise barriers for Bay NB16-07P |  |  | $
20.3.1.8 | Completion of installation of vertical posts of noise barriers for Bay NB16-08P |  |  | $
20.3.1.9 | Completion of installation of vertical posts of noise barriers for Bay NB16-09P |  |  | $
20.3.1.10 | Completion of installation of vertical posts of noise barriers for Bay NB16-10P |  |  | $
20.3.1.11 | Completion of installation of vertical posts of noise barriers for Bay NB16-11P |  |  | $
20.3.1.12 | Completion of installation of vertical posts of noise barriers for Bay NB16-12P |  |  | $
20.3.1.13 | Completion of installation of vertical posts of noise barriers for Bay NB16-13P |  |  | $
20.3.1.14 | Completion of installation of vertical posts of noise barriers for Bay NB16-14P |  |  | $
20.3.1.15 | Completion of installation of vertical posts of noise barriers for Bay NB16-15P |  |  | $
20.3.1.16 | Completion of installation of vertical posts of noise barriers for Bay NB16-16P |  |  | $
20.3.1.17 | Completion of installation of vertical posts of noise barriers for Bay NB16-17P |  |  | $
20.3.1.18 | Completion of installation of vertical posts of noise barriers for Bay NB16-18P |  |  | $
20.3.1.19 | Completion of installation of vertical posts of noise barriers for Bay NB16-19P |  |  | $
20.3.1.20 | Completion of installation of vertical posts of noise barriers for Bay NB16-20P |  |  | $
20.3.1.21 | Completion of installation of vertical posts of noise barriers for Bay NB16-21P |  |  | $
20.3.1.22 | Completion of installation of vertical posts of noise barriers for Bay NB16-22P |  |  | $
20.3.2 | Installation of tie beams for noise barriers
20.3.2.1 | Completion of installation of tie bems of noise barriers for Bay NB16-01P |  |  | $
20.3.2.2 | Completion of installation of tie bems of noise barriers for Bay NB16-02P |  |  | $
20.3.2.3 | Completion of installation of tie bems of noise barriers for Bay NB16-03P |  |  | $
20.3.2.4 | Completion of installation of tie bems of noise barriers for Bay NB16-04P |  |  | $
20.3.2.5 | Completion of installation of tie bems of noise barriers for Bay NB16-05P |  |  | $
20.3.2.6 | Completion of installation of tie bems of noise barriers for Bay NB16-06P |  |  | $
20.3.2.7 | Completion of installation of tie bems of noise barriers for Bay NB16-07P |  |  | $
20.3.2.8 | Completion of installation of tie bems of noise barriers for Bay NB16-08P |  |  | $
20.3.2.9 | Completion of installation of tie bems of noise barriers for Bay NB16-09P |  |  | $
20.3.2.10 | Completion of installation of tie bems of noise barriers for Bay NB16-10P |  |  | $
20.3.2.11 | Completion of installation of tie bems of noise barriers for Bay NB16-11P |  |  | $
20.3.2.12 | Completion of installation of tie bems of noise barriers for Bay NB16-12P |  |  | $
20.3.2.13 | Completion of installation of tie bems of noise barriers for Bay NB16-13P |  |  | $
20.3.2.14 | Completion of installation of tie bems of noise barriers for Bay NB16-14P |  |  | $
20.3.2.15 | Completion of installation of tie bems of noise barriers for Bay NB16-15P |  |  | $
20.3.2.16 | Completion of installation of tie bems of noise barriers for Bay NB16-16P |  |  | $
20.3.2.17 | Completion of installation of tie bems of noise barriers for Bay NB16-17P |  |  | $
20.3.2.18 | Completion of installation of tie bems of noise barriers for Bay NB16-18P |  |  | $
20.3.2.19 | Completion of installation of tie bems of noise barriers for Bay NB16-19P |  |  | $
20.3.2.20 | Completion of installation of tie bems of noise barriers for Bay NB16-20P |  |  | $
20.3.2.21 | Completion of installation of tie bems of noise barriers for Bay NB16-21P |  |  | $
20.3.2.22 | Completion of installation of tie bems of noise barriers for Bay NB16-22P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
20.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
20.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Barrier NB16 (Bay NB16-01P to 22P) |  | $
20.5 | Miscellanous
20.5.1 | Completion of installation of drainage |  |  | $
20.5.2 | Completion of installation of watermains |  |  | $
20.5.3 | Completion of diversion of existing utilities |  |  | $
20.5.4 | Completion of reinstatement of existing footpath |  |  | $
20.5.5 | Completion of reinstatement of carriageway |  |  | $
20.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S20/1 |  |  | $
| Collection from Page AS.S20/2 |  |  | $
| Collection from Page AS.S20/3 |  |  | $
| Collection from Page AS.S20/4 |  |  | $
| Collection from Page AS.S20/5 |  |  | $
| Collection from Page AS.S20/6 |  |  | $
|  |  | Total Prices of Schedule No. 20 Carried to Grand Summary of the Activity Schedule | $

## A21 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 21 - Noise Semi-enclosure SE01
Item | Activity |  |  | Prices (HK$)
21 | Noise Semi-enclosure SE01
21.1 | Piling Works
21.1.1 | Establishment of piling plant |  |  | $
21.1.2 | Pre-drilling works |  |  | $
21.1.3 | Piling
21.1.3.1 | Excavation of piles
21.1.3.1.1 | Completion of excavation of piles for Bay SE01-01P |  |  | $
21.1.3.1.2 | Completion of excavation of piles for Bay SE01-02P |  |  | $
21.1.3.1.3 | Completion of excavation of piles for Bay SE01-03P |  |  | $
21.1.3.1.4 | Completion of excavation of piles for Bay SE01-04P |  |  | $
21.1.3.1.5 | Completion of excavation of piles for Bay SE01-05P |  |  | $
21.1.3.1.6 | Completion of excavation of piles for Bay SE01-101P |  |  | $
21.1.3.1.7 | Completion of excavation of piles for Bay SE01-102P |  |  | $
21.1.3.1.8 | Completion of excavation of piles for Bay SE01-103P |  |  | $
21.1.3.1.9 | Completion of excavation of piles for Bay SE01-104P |  |  | $
21.1.3.1.10 | Completion of excavation of piles for Bay SE01-105P |  |  | $
21.1.3.2 | Installation of reinforcement for piles
21.1.3.2.1 | Completion of installation of reinforcement of piles for Bay SE01-01P |  |  | $
21.1.3.2.2 | Completion of installation of reinforcement of piles for Bay SE01-02P |  |  | $
21.1.3.2.3 | Completion of installation of reinforcement of piles for Bay SE01-03P |  |  | $
21.1.3.2.4 | Completion of installation of reinforcement of piles for Bay SE01-04P |  |  | $
21.1.3.2.5 | Completion of installation of reinforcement of piles for Bay SE01-05P |  |  | $
21.1.3.2.6 | Completion of installation of reinforcement of piles for Bay SE01-101P |  |  | $
21.1.3.2.7 | Completion of installation of reinforcement of piles for Bay SE01-102P |  |  | $
21.1.3.2.8 | Completion of installation of reinforcement of piles for Bay SE01-103P |  |  | $
21.1.3.2.9 | Completion of installation of reinforcement of piles for Bay SE01-104P |  |  | $
21.1.3.2.10 | Completion of installation of reinforcement of piles for Bay SE01-105P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
21.1.3.3 | Completion of piling works
21.1.3.3.1 | Completion of all piling works for Bay SE01-01P |  |  | $
21.1.3.3.2 | Completion of all piling works for Bay SE01-02P |  |  | $
21.1.3.3.3 | Completion of all piling works for Bay SE01-03P |  |  | $
21.1.3.3.4 | Completion of all piling works for Bay SE01-04P |  |  | $
21.1.3.3.5 | Completion of all piling works for Bay SE01-05P |  |  | $
21.1.3.3.6 | Completion of all piling works for Bay SE01-101P |  |  | $
21.1.3.3.7 | Completion of all piling works for Bay SE01-102P |  |  | $
21.1.3.3.8 | Completion of all piling works for Bay SE01-103P |  |  | $
21.1.3.3.9 | Completion of all piling works for Bay SE01-104P |  |  | $
21.1.3.3.10 | Completion of all piling works for Bay SE01-105P |  |  | $
21.1.4 | Pile tests
21.1.4.1 | Completion of all pile tests |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
21.2 | Substructure
21.2.1 | Excavation for pile cap
21.2.1.1 | Completion of excavation of pile cap for Bay SE01-01P |  |  | $
21.2.1.2 | Completion of excavation of pile cap for Bay SE01-02P |  |  | $
21.2.1.3 | Completion of excavation of pile cap for Bay SE01-03P |  |  | $
21.2.1.4 | Completion of excavation of pile cap for Bay SE01-04P |  |  | $
21.2.1.5 | Completion of excavation of pile cap for Bay SE01-05P |  |  | $
21.2.1.6 | Completion of excavation of pile cap for Bay SE01-101P |  |  | $
21.2.1.7 | Completion of excavation of pile cap for Bay SE01-102P |  |  | $
21.2.1.8 | Completion of excavation of pile cap for Bay SE01-103P |  |  | $
21.2.1.9 | Completion of excavation of pile cap for Bay SE01-104P |  |  | $
21.2.1.10 | Completion of excavation of pile cap for Bay SE01-105P |  |  | $
21.2.2 | Fixing of reinforcement
21.2.2.1 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-01P |  |  | $
21.2.2.2 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-02P |  |  | $
21.2.2.3 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-03P |  |  | $
21.2.2.4 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-04P |  |  | $
21.2.2.5 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-05P |  |  | $
21.2.2.6 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-101P |  |  | $
21.2.2.7 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-102P |  |  | $
21.2.2.8 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-103P |  |  | $
21.2.2.9 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-104P |  |  | $
21.2.2.10 | Completion of fixing of reinforcement of pile cap and stem wall for Bay SE01-105P |  |  | $
21.2.3 | Completion of pile caps with stem wall
21.2.3.1 | Completion of all pile caps with stem wall and movement joints for Bay SE01-01P |  |  | $
21.2.3.2 | Completion of all pile caps with stem wall and movement joints for Bay SE01-02P |  |  | $
21.2.3.3 | Completion of all pile caps with stem wall and movement joints for Bay SE01-03P |  |  | $
21.2.3.4 | Completion of all pile caps with stem wall and movement joints for Bay SE01-04P |  |  | $
21.2.3.5 | Completion of all pile caps with stem wall and movement joints for Bay SE01-05P |  |  | $
21.2.3.6 | Completion of all pile caps with stem wall and movement joints for Bay SE01-101P |  |  | $
21.2.3.7 | Completion of all pile caps with stem wall and movement joints for Bay SE01-102P |  |  | $
21.2.3.8 | Completion of all pile caps with stem wall and movement joints for Bay SE01-103P |  |  | $
21.2.3.9 | Completion of all pile caps with stem wall and movement joints for Bay SE01-104P |  |  | $
21.2.3.10 | Completion of all pile caps with stem wall and movement joints for Bay SE01-105P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
21.3 | Superstructure
21.3.1 | Installation of vertical posts for noise semi-enclosure
21.3.1.1 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-01P |  |  | $
21.3.1.2 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-02P |  |  | $
21.3.1.3 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-03P |  |  | $
21.3.1.4 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-04P |  |  | $
21.3.1.5 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-05P |  |  | $
21.3.1.6 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-101P |  |  | $
21.3.1.7 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-102P |  |  | $
21.3.1.8 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-103P |  |  | $
21.3.1.9 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-104P |  |  | $
21.3.1.10 | Completion of installation of vertical posts of noise semi-enclosure for Bay SE01-105P |  |  | $
21.3.2 | Installation of main beams for noise semi-enclosure
21.3.2.1 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-01P |  |  | $
21.3.2.2 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-02P |  |  | $
21.3.2.3 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-03P |  |  | $
21.3.2.4 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-04P |  |  | $
21.3.2.5 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-05P |  |  | $
21.3.2.6 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-101P |  |  | $
21.3.2.7 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-102P |  |  | $
21.3.2.8 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-103P |  |  | $
21.3.2.9 | Completion of installation of mainb beams of noise semi-enclosure for Bay SE01-104P |  |  | $
21.3.2.10 | Completion of installation of main beams of noise semi-enclosure for Bay SE01-105P |  |  | $
21.3.3 | Installation of tie beams for noise semi-enclosure
21.3.3.1 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-01P |  |  | $
21.3.3.2 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-02P |  |  | $
21.3.3.3 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-03P |  |  | $
21.3.3.4 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-04P |  |  | $
21.3.3.5 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-05P |  |  | $
21.3.3.6 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-101P |  |  | $
21.3.3.7 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-102P |  |  | $
21.3.3.8 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-103P |  |  | $
21.3.3.9 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-104P |  |  | $
21.3.3.10 | Completion of installation of tie beams of noise semi-enclosure for Bay SE01-105P |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
21.4 | Contractor's Design
Tenderer is required to complete a detailed Schedule of Rates in accordance with ACC Clause F2(9) for the
Contractor's Design for the following item(s):
21.4.1 |  | Noise Barrier Panels and Sub-frames for Noise Semi-enclosure SE01 (Bay SE01-01P to 05P, 101P to 105P) |  | $
21.4.2 |  | Photovoltaic (PV) System for Noise Semi-enclsoure SE01 |  | $
21.5 | Miscellanous
21.5.1 | Completion of installation of drainage |  |  | $
21.5.2 | Completion of installation of watermains |  |  | $
21.5.3 | Completion of diversion of existing utilities |  |  | $
21.5.4 | Completion of reinstatement of existing footpath |  |  | $
21.5.5 | Completion of reinstatement of carriageway |  |  | $
21.6 | Additional items required by the Contractor (to be inserted by rhe Contractor) |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S21/1 |  |  | $
| Collection from Page AS.S21/2 |  |  | $
| Collection from Page AS.S21/3 |  |  | $
| Collection from Page AS.S21/4 |  |  | $
| Collection from Page AS.S21/5 |  |  | $
|  |  | Total Prices of Schedule No. 21 Carried to Grand Summary of the Activity Schedule | $ | 0

## A25 (hidden)
THE GOVERNMENT OF THE HONG KONG SPECIAL ADMINISTRATIVE REGION
HIGHWAYS DEPARTMENT
MAJOR WORKS PROJECT MANAGEMENT OFFICE
CONTRACT NO. HY/2021/06
RETROFITTING OF NOISE BARRIERS ON PO LAM ROAD NORTH AND PO NING ROAD
ACTIVITY SCHEDULE
Schedule No. 25 - Geotechnical Works
Item | Activity |  |  | Prices (HK$)
25.1 | Slopeworks
25.1.1 | Sub-soil drains
25.1.1.1 |  | perforated polyethelene pipe; 50mm diameter |  | $
25.1.1.2 |  | UPVC pipe; 50mm diameter |  | $
25.1.1.3 |  | U-channel; 225mm diameter without cover |  | $
25.1.1.4 |  | U-channel; 300mm diameter without cover |  | $
25.1.1.5 |  | U-channel; 375mm diameter without cover |  | $
25.1.1.6 |  | U-channel; 450mm diameter without cover |  | $
25.1.1.7 |  | stepped channel with apron; 300mm diameter |  | $
25.1.2 | Granular filters
25.1.2.1 |  | grade 75 |  | $
25.1.3 | Geotextile filters
25.1.3.1 |  | "Miradrain 5000" or product with equivalent performance |  | $
25.1.3.2 |  | non-woven polyprolene |  | $
25.1.4 | Earthworks
25.1.4.1 |  | general excavation |  | $
25.1.4.2 |  | deposition of general fill material |  | $
25.1.4.3 |  | disposal of material |  | $
25.1.4.4 |  | compaction of general fill material |  | $
25.1.5 | Concrete
25.1.1.1 |  | no-fines concrete |  | $
25.1.6 | Erosion Control Mats |  |  | $
25.1.7 | Wire mesh |  |  | $
|  |  | Total carried to collection | $
Item | Activity |  |  | Prices (HK$)
| Collection from Page AS.S25/1 |  |  | $
|  |  | Total Prices of Schedule No. 25 Carried to Grand Summary of the Activity Schedule | $